## MPR 1.3_Project under progress
(April 2025 - March 2026)
For the month (As on 30th March 2026)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | COD declared - 04/03/2026
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
9 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partially COD declared
10 | I&D with STP works at Sapera Basti, Dehradun | DBOT | 78.99 | 15 |  | Under trial operations
11 | I & D and STP works at Muni ki reti, Neelkanth, Swarg aashram | DBOT | 94.06 | 12.8 |  | Under trial operations (Muni-Ki-Reti and Swargashram) Under Construction (Neelkanth)
12 | Interception and diversion of balance discharge of 13 drains and augmentation of Salori STP | DBOT | 331.75 | 43 |  | Under trial operations
13 | I&D and STP Works at Vrindavan | DBOT | 77.7 | 13 |  | Under trial operations
14 | I&D and STP Works for Assi-BHU Area (Phase II), Varanasi, Uttar Pradesh’ under Namami Gange Programme | DBOT | 308.09 | 55 |  | Completed. O&M Statrt Date - 17/03/2026
15 | I & D and STP Project at Phusro | DBOT | 61.05 | 14 | 10 MLD - Trial started on 15th Jan 2026. 4 MLD- Trial run started on 16th Feb 2026
16 | Interception and Diversion with STP) at Chakdah Municipal Town | DBOT | 121.66 | 15 | trial run started on 14th Feb 2026.
17 | Pollution Abatement Works for River Ganga at North Barrackpore municipality | HAM | 154.27 | 38 | 30 MLD- under trial run since 15.12.2025.
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date to be declared by 31st May 2026. Pending Conditions precedent include (i) BEP Approval; (ii) Construction Plan approval; (iv) Phase I design drawing Submission; (v) Escrow Agreement. Site survey, soil investigations, site clearing completed. Site level variations (Actual vs RFP) reported in the review meeting held on 25/02/2026 Basin excavation and retaining wall work started
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | Effective date for STP-1 ,2&3 has been declared as 02.03.2026. | Due to pending land NOC the effective date for remaining STPs (STP-4 &5) is yet to be declared.

## MPR 1.4_KSDC
April 2025 - March 2026
For the month of March 2026
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | Till February, 2026 | March, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 3 | 3 | 6
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) March
S.No | Event Topic | Type | Venue | Date/Days/ Duration | No. of Participants
1 | Fourth training program of the Knowledge-cum-Skill Development Centre (KSDC) for Yamuna Task Force at Yamuna Biodiversity Park by the Centre for Environmental Management of Degraded Ecosystems (CEMDE) | 2 | Offline (Yamuna Biodiversity Park) | 09.03.2026- 11.03.2026 | 10
2 | Fifth Training program of the Knowledge-cum-Skill Development Centre (KSDC) for District Ganga Committees (DGCs) of Uttarakhand at Yamuna Biodiversity Park by the Centre for Environmental | 2 | Offline (Yamuna Biodiversity Park) | 18.03.2026- 20.03.2026 | 13
3 | Sixth Training program of the Knowledge-cum-Skill Development Centre (KSDC) for District Ganga Committees (DGCs) of Uttarakhand at Yamuna Biodiversity Park by the Centre for Environmental | 2 | Offline (Yamuna Biodiversity Park) | 25.03.2026-27.03.2026 | 7
List (Type 1,6) March
| Sl. No. | Subject |  | Date
List (Type 7) March
| Sl. No. | Subject |  | Date
1
2

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of March, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Feb-26 | 2026-03-01
1 | STP Inspection Reports Received **
| Uttrakhand | Aug'25 - Nov'25 | -
| Uttar Pradesh | Aug'25 - Nov'25 | -
| Bihar | Aug'25 - Nov'25 | -
| Jharkhand | Aug'25 - Nov'25 | -
| West Bengal | Aug'25 - Nov'25 | -
2 | River water Quality Data Received *
| Uttrakhand | Jul'25- Sep'2025 | -
| Uttar Pradesh | Jul'25- Sep'2025 | -
| Bihar | Jul'25- Sep'2025 | -
| Jharkhand | Jul'25- Sep'2025 | -
| West Bengal | Jul'25- Sep'2025 | -
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3703 (Ganga: 1296; Yamuna: 2407) | 3703 | 3703
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Sep'2025 | -
| Uttar Pradesh | Jan'25- Sep'2025 | -
| Bihar | Jan'25- Sep'2025 | -
| Jharkhand | Jan'25- Sep'2025 | -
| West Bengal | Jan'25- Sep'2025 | -
5 | Number of Publications/Reports | 37 | 5
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB informed to NMCG 'In the matter of Arbitration between CPCB and JV of two entities engaged for the project of Continuous RTWQM Data Procurement from 36 River Ganga locations', funded by NMCG | 2026-03-13
2 | Finalization of cost estimates and technical institutes for ninth round of Annual inspection of Grossly Polluting Industries (GPIs) 2026 (PIAS). | 2026-03-16
3 | CPCB Report of 52 Yamuna Drains monitoring (May2025-Jan'2026) | 2026-03-18
4 | CPCB submitted updated data on Biomonitoring on Ganga and Yamuna alongwith its tributaries (2025-26 Premonsoon) | 2026-03-20
5 | CPCB letter for guidance on 40 RTWQMs | 2026-03-24
Annexure A for S.No 3
| Total GPIs | 3703
| Inspected | 3703
| Complied | 2479 | << Total Action Completed Till date
| Non-Complied | 598 | << Total Action Completed Till date
| Temporary Closed | 403 | << Total Action Completed Till date
| Permanently Closed | 98 | << Total Action Completed Till date

## MPR 3.2_Regulatory Cell
(April 2025 - March 2026)
For the month of March (As on 31st March 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of Feb 25 | 13
2 | Application returned back in March 26 | 2
3 | Applications decided in March 26 | 0
4 | New Applications received in March 26 | 2
5 | Pending Application at the end of March 26 | 13
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Dec 2025) | 2
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/ Return | Cases Recommended
| 0 | 0 | 0 | 0
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Discharge of Treated Effluent from MDA operated STPs into Chap Salawa Minor under the 220 MLD STP Project, Meerut | Chief Engineer, UP Jal Nigam (Rural) | 2025-10-29 | File with project wing, sought clarification from state
2 | Renewal for 7 years Ram anubhav kendra | Ayodhaya Development Authority | 2025-07-02 | File pending at competant authority for decision

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
1st March 2026 to 31st March 2026 | 0
Total | 522
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Total: 69
Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01
Wing/Section/ Unit wise summary from 1st March 2026 till 31st March 2026
i. Nill

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (March 2026)
Generated on 31st March 2026
Sl. No. | Title | Till 28th February 2026 | 2026-03-01 | Total (as on 30th March 2026)
1 | Total Number Document on GKP | 1346 | 25 | 1371
2 | Other Literature on River Ganga | 10226 | 90 | 10316
Categories-wise details of documents uploaded between 1st to 31st March 2026
Categories | Sub-categories | No. of documents
Publications |  | 2
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 2
Studies/Reports |  | 3
sGuidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 1
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 17
Total |  | 25
Details of documents uploaded between 1st to 31st March 2026
S.No | Category | Subject | Organization
1 | Reports | Environmental Flows of Major Rivers in Uttar Pradesh | WWF-India
2 | Books | Know your glaciers in ganga basin | National Institute of Hydrology, Roorkee (NIH)
3 | Reports | Ecological Assessment of the Chambal River : Status of Major Aquatic Fauna and Flow Requirements | WII
4 | Reports | Snow cover Atlas of the Ganga basin | Space Applications Centre, Indian Space Research Organisation (ISRO)
5 | Books | Monitoring Snow and Glaciers of Himalayan Region | Space Applications Centre, Indian Space Research Organisation (ISRO)
6 | Publications | Inventory of The Himalayan Glaciers A Contribution to the International Hydrological Programme (Third Edition) | Geological Survey of India (GSI)
7 | Publications | Ganga River Basin Management Plan 2 (framework) | cGanga
8 | River Atlas | River Atlas - Kanpur Nagar | cGanga
9 | River Series | Terhi river | WII
10 | River Series | Sot river | WII
11 | River Series | Sengar river | WII
12 | River Series | Sarayan river | WII
13 | River Series | Parbati river | WII
14 | River Series | Kunwari river | WII
15 | River Series | Kanhar river | WII
16 | River Series | Kangsabati river | WII
17 | River Series | Kali Sindh river | WII
18 | River Series | Kali river | WII
19 | River Series | Isan river | WII
20 | River Series | Hooghly river | WII
21 | River Series | Gopad river | WII
22 | River Series | Ganga river | WII
23 | River Series | East Bahgul river | WII
24 | River Series | Chhoti Sarju river | WII
25 | River Series | Arind river | WII

## MPR 5.3-Prayag status
(April 2025 - March 2026)
For the month of March (As on 31st Mar 26)
MPR Prayag/GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status*
a | No. of STPs with OCEMS Installed | 274*
b | No. of STPs with Flow Data received | 164
c | No. of STPs with Influent Characteristic Data received # | 146
d | No. of STPs with Effluent Characteristic Data received | 206
2 | Data Reliability Status **
a | No. of STPs with Satisfactory Data received | 212
b | No. of STPs with Poor Data Quality (Annex A1) ** | 8
c | No. of STPs with No Data Received (Annex A2) | 37
B | OCEMS based Results communicated to States till Month | Communicated till March-2026
C | Eflows report updated till period | Updated till December 2025
D | GDPMS
| No. of Meetings held in January 2026 | 108
| No. of Meetings held in February 2026 | 93
| No. of Meetings held in March 2026 | 28
E | Prayag GEO Portal
| No. of Active GIS Layers (Annex B) | 30
| No. of Use Cases | 7
PRAYAG/ Geoportal-MPR March 2026 (Item 5.3, MPR)
Note (*): A total of seven STPs and three outlet sites have been decommissioned. In their place, ten new STPs have been added to the project scope. Accordingly, the number of STPs reflected in this month’s MPR has reduced.
No. of STPs with Poor Data Quality (Annex A1) **
S.No | STP | Site Location | State | Address | Last Seen | Offline Reason
1 | 130 MLD STP Jajmau Kanpur | Inlet | Uttar Pradesh | à¤•à¤¾à¤¨à¤ªà¥à¤°, Kanpur Nagar, Uttar Pradesh, India | 23 Jan 2026, 05:17 pm | Under Maintenance
2 | 33 MLD STP Ayodhya | Inlet | Uttar Pradesh | 33 MLD STP Plant, Manjha Kala, Ayodhya Divison, Uttarpradesh-224001 | 11 Jan 2026, 07:14 am | Internet issue
3 | 1.5 MLD STP Anupshahar (UPJN) | Outlet | Uttar Pradesh | Anupshahar, Uttar Pradesh | 07 Jan 2026, 04:38 pm | -
4 | 33 MLD STP Ayodhya | Outlet | Uttar Pradesh | 33 MLD STP Plant, Manjha Kala, Ayodhya Divison, Uttarpradesh-224001 | 05 Jan 2026, 10:29 am | internet issue
5 | 8 MLD STP MOKAMA BIHAR | Inlet | Bihar | MARO POKHAR, MOKAMA, PO MOKAMA, PS MOKAMA, DIST. PATNA, BIHAR | 02 Jan 2026, 02:16 pm | -
6 | 1 MLD STP Gangotri | Inlet | Uttarakhand | Gangotri, Uttarkashi | 30 Dec 2025, 10:56 am | Seasonal Downtime
7 | 1 MLD STP Gangotri | Outlet | Uttarakhand | Gangotri, Uttarkashi | 30 Dec 2025, 10:54 am | Seasonal Downtime
8 | 10 MLD STP Kalyani 2 | Outlet | West Bengal | 10 MLD STP at Kalyani 2 | 25 Sept 2025, 12:30 pm | Under Maintenance
9 | 10.4 MLD STP Bokaro | Outlet | Jharkhand | Bokaro | 02 Sept 2025, 06:04 pm | Under Maintenance
No. of STPs with No Data Received (Annex A2)
S.No | Sewage Treatment Plant | Status | District | Address | State
1 | 30 MLD STP Pachahatiya | Offline | Jaunpur | Pachahatiya, Jaunpur, 222002 | Uttar Pradesh
2 | 26.5 MLD STP at Chinsurah | Offline | Hugli | 26.5 MLD STP at Chinsurah, West Bengal-712101 | West Bengal
3 | 140 MLD STP Dinapur | Offline | Varanasi | 140 MLD STP at Dinapur ,varanasi | Uttar Pradesh
4 | 22 MLD STP Uttarapara | Offline | Hooghly | 22 MLD STP at Uttarapara | West Bengal
5 | 1.5 MLD STP Chutia | Offline | Ranchi | 1.5 MLD STP at Chutia Ranchi | Jharkhand
6 | 15 MLD STP Kasganj | Offline | Kasganj | Kasganj, UP Jal Nigam, Kasganj, 207123 | Uttar Pradesh
7 | 12 MLD STP BLW Varanasi | Offline | varanasi | varanasi uttar pradesh | Uttar Pradesh
8 | 21 MLD STP Pakka Bagh | Offline | Etawah | Pakka Bagh near Brahm Nagar, Umrain, Etawah | Uttar Pradesh
9 | 6 MLD STP Baidyavati | Offline | Hooghly | 6 MLD STP at Baidyavati | West Bengal
10 | 18 MLD STP Kachanpara | Offline | North 24 Parganas | 18 MLD STP at Kachanpara | West Bengal
11 | 13.50 MLD STP Tixi Nala | Offline | Etawah | Near Tixi Temple, Etawah | Uttar Pradesh
12 | 6.5 MLD STP Naihati | Offline | North 24 Parganas | 6.5 MLD STP at Naihati | West Bengal
13 | 1.5 MLD STP Harmu | Offline | Ranchi | 1.5 MLD STP at Harmu, Ranchi | Jharkhand
14 | 1.0 MLD STP Badrinath | Offline | Chamoli | Badrinath, Joshimath Tehsil, Chamoli, Uttarakhand, India | Uttarakhand
15 | 60 MLD STP Baranagar | Offline | Ganga District | Baranagar, Barrackpore, North 24 Parganas, West Bengal, 700035, India | West Bengal
16 | 40 MLD STP at Bally Howarh | Offline | Ganga District | Bally, Bally Jagachha, Howrah, West Bengal, 712258, India | West Bengal
17 | 120 MLD STP Goitha Varanasi | Offline | Varanasi | Varanasi, Sadar, Varanasi, Uttar Pradesh, 221001, India | Uttar Pradesh
18 | 1.25 MLD STP Chamoli Gopeshwar | Offline | Chamoli | Gopeshwar, Chamoli Tehsil, Chamoli, Uttarakhand, 246401, India | Uttarakhand
19 | 65 MLD STP Arupara Howrah | Offline | Ganga District | Arupara, West Bengal | West Bengal
20 | 10 MLD STP A2O Ramnagar | Offline | Varanasi | Varanasi, Sadar, Varanasi, Uttar Pradesh, 221001, India | Uttar Pradesh
21 | 30 MLD STP JAUNPUR | Offline | Jaunpur | Jaunpur, Uttar Pradesh, 222001, India | Uttar Pradesh
22 | 15 MLD STP Kairana | Offline | Shamli | Kairana, Shamli, Uttar Pradesh, 247774, India | Uttar Pradesh
23 | 16 MLD STP Laxmi Nagar UASB | Offline | Mathura | Mathura, Uttar Pradesh, 281001, India | Uttar Pradesh
24 | 14.5 MLD STP Laxmi Nagar | Offline | Mathura | Mathura, Uttar Pradesh, 281001, India | Uttar Pradesh
25 | 30 MLD STP Masani | Offline | Mathura | Mathura, Uttar Pradesh, 281001, India | Uttar Pradesh
26 | 6.8 MLD STP Masani | Offline | Mathura | Mathura, Uttar Pradesh, 281001, India | Uttar Pradesh
27 | 100 MLD STP at Noida Sector 168 | Offline | Gautam Buddh Nagar | Noida, Dadri, Gautam Buddh Nagar, Uttar Pradesh, India | Uttar Pradesh
28 | 1.19 MLD STP EC Gopeshwar Chamoli | Offline | Chamoli | Gopeshwar, Chamoli Tehsil, Chamoli, Uttarakhand, 246401, India | Uttarakhand
29 | 7 MLD STP Mirzapur | Offline | Mirzapur | Mirzapur, Uttar Pradesh, 231001, India | Uttar Pradesh
30 | 15 MLD STP Baniyapur UPJN | Offline | Kanpur | Kanpur Nagar, Uttar Pradesh, India | Uttar Pradesh
31 | 4 MLD STP Vrindavan | Offline | Mathura | Vrindavan, Mathura, Uttar Pradesh, 281121, India | Uttar Pradesh
32 | 1.12 MLD STP Dindayal Upadhyay | Offline | Chamoli | Chamoli, Chamoli Tehsil, Chamoli, Uttarakhand, 246426, India | Uttarakhand
33 | 20 MLD CETP Jajmau | Offline | kanpur | Kanpur Nagar, Uttar Pradesh, India | Uttar Pradesh
34 | 9.5 MLD STP Nawadwip | Offline | North 24 Parganas | Nawadwip, West Bengal | West Bengal
35 | 10.445 MLD STP Etawah | Offline | Etawah | Etawah, Uttar Pradesh, 206001, India | Uttar Pradesh
36 | 14Â MLD STP Baghpat | Offline | Baghpat | Baghpat, Uttar Pradesh, 250609, India | Uttar Pradesh
37 | 21 MLD STP ETAWAH | Offline | Etawah | Etawah, Uttar Pradesh, 206001, India | Uttar Pradesh
Annexure-B Active GIS layer -March 2026 (As on 30.03.2026)
S. No. | Type | GIS Layer
1 | BASIC | Ganga
2 |  | Ganga Centre line SoI
3 |  | Popular River
4 |  | Ganga River Basin
5 |  | Ganga State
6 |  | Ganga Basin Sub District Census
7 |  | Ganga Basin Town Census
8 |  | Census Sub District 2011
9 |  | Census Town 2011
10 | WATER RESOURCES | India River Network
11 |  | Major Aquifers
12 | ECOLOGY | Riverine Wetland (UP/Bihar/ Jharkhand)
13 | RIVER WATER QUALITY | Ganga Polluted Stretch, 2018
14 |  | Ganga Polluted Stretch, 2022
15 |  | Ganga Polluted Stretch, 2023
16 |  | Ganga Polluted Stretch, 2025
17 |  | Manual Water Quality Stations (Locations)
18 |  | RTQMS (Locations)
19 |  | Biomonitoring (Locations) (to be add)
20 | POLLUTION ASPECTS | Sewage Gap Analysis
21 |  | STP (Other than NMCG) (Locations)
22 |  | STP NMCG (Locations)
23 |  | GPIs (Locations)
24 |  | Solid Waste Dumps (IIRS data)
25 | MISC. | Ganga Centre line 1 km points SoI
26 |  | Ganga Final Survey SoI
27 |  | Point outfall 45N SoI
28 |  | Point outfall 44N SoI

## MPR 5.4-Jan Ganga Vertical_Comm
(April 2025 - March 2026)
For the Month of March 2026 (As on 1st April 2026)
MPR Communication
| Followers | Till previous Month (February 2026 ) | Current Month (March 2026)
1 | Twitter | 123184 | 122686
| Facebook | 532515 | 542672
| Instagram | 113293 | 116408
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 285 | 37 Videos | 64 mins
| Facebook | 272 | 49 Videos | 88 mins
| Instagram | 152 | 41 Videos | 60 Mins
b) | Rebuttals on
Social Media
c) | Positive Stories |  |  | Annex A
| Social Media | 11 Postive Stories
3 | Youtube
4 | Print Media
a) | Rebutted
b) | Positive Stories | 12 |  | Annex A
5 | Publication through PIB
a) | Press Release ( Atleast One per month )
i) | Press Release-Event Based | 21st Central Monitoring Committee Meeting PIB Press Release | 2nd March, 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2234673&reg=3&lang=1
ii) | Press Release- Success Story | Safe Reuse of Treated Water PIB Press Release | 17th March, 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2241229&reg=3&lang=2
b) | Backgrounder ( One per Quarter ) | Nil
c) | Articles/Op-eds in Newspapers ( One article -Half Yearly) | Nil
|  | Number of Events | Participation
6 | Events Organised by NMCG |  |  | Annex B
a) | Cleanliness Drives on Yamuna | 4 | Approx. 2000
b) | Workshop on Groundwater & Surface Water - 7th March 2026 | 1 | 200
c) | Workshop onConserving Himalayan Glacier - 23rd March 2026 | 1 | 50
d) | Workshop on Sludge Reuse - 23rd March 2026 | 1 | 500
7 | Events through Partner |  |  | Annex B
a) | DGC & SMCG | 279
b) | NGO | 22
c) | Institutes | 19
| Total | 320 | Approx. 92915
8 | Sponsorship
a) | Jal Yodha Samman Samaroh ( 28th March ) | 200 | VIP: Sri Sri Ravishankar Padmshree Awardee
b) | Water Digest Water Awards ( 23rd March 2026 ) | 300 | VIP " Hon'ble Jal Shakti Minister , MoS Jal Shakti
9 | Capacity Building Training /Workshop (Communication Unit ) | Nil
Annex B
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | Jal Saheli | 2026-03-27 | https://x.com/i/status/2037393830757220487 | https://fb.watch/G9NH9zCgxQ/ | https://www.instagram.com/reel/DWYHFjbDOxl/?igsh=MXF1d3RsNGV3amN4cw==
2 | Public Review, Banaras | 2026-03-26 | https://x.com/i/status/2037057475179102595 | https://www.facebook.com/reel/2847819182230611 | https://www.instagram.com/reel/DWVoxicD7KH/?igsh=OGsxeHJ1MDZmemcz
3 | Vrindavan STP Update | 2026-03-25 | https://x.com/i/status/2036753430673608978 | https://fb.watch/G9OtHHWhQT/ | https://www.instagram.com/reel/DWTekbMDA7q/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
4 | Maner STP | 2026-03-25 | https://www.instagram.com/reel/DWTTPcsjMFm/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA== | https://fb.watch/G9OWKPc7W0/ | https://x.com/i/status/2036729065319940579
5 | Public Review ( Sisamau Nala) | 2026-03-19 | https://x.com/i/status/2034523928836940219v | https://www.facebook.com/reel/26770161985942307 | https://www.instagram.com/reel/DWDogfmE9Iz/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
6 | Bhadra Ghat, Patna | 2026-03-12 | https://x.com/i/status/2032090319747944539 | https://fb.watch/G9PfvGgLa4/ | https://www.instagram.com/reel/DVyVxKQj9VJ/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
7 | Public Review Prayagraj | 2026-03-12 | https://x.com/i/status/2032078155528487429 | https://www.facebook.com/reel/26033682562962340 | https://www.instagram.com/reel/DVyRqyaj6dn/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
8 | Rishikesh Ganga flow | 2026-03-12 | https://x.com/i/status/2032040762079396278 | https://fb.watch/G9PKKhu_Cd/ | https://www.instagram.com/reel/DVx_yoTDFqJ/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
9 | Muni ki Reti STP | 2026-03-10 | https://x.com/i/status/2031323010892980296 | https://fb.watch/G9QgM7_Six/ | https://www.instagram.com/reel/DVs5Eenktba/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
10 | Public Review Banaras | 2026-03-09 | https://x.com/i/status/2030952955864879283 | https://fb.watch/G9QerNPQoI/ | https://www.instagram.com/reel/DVqQ6KLDKi5/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
11 | Ghariyal Spotted in Kanpur | 2026-03-06 | https://x.com/i/status/2029851169083031867 | https://www.facebook.com/reel/1625407485270054 | https://www.instagram.com/reel/DViZ2AmjFHS/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
12 | Jal Shakta Ministry panel reviews status of polluted river stretches | 3rd March, 2026
13 | Shri CR Paatil urges citizen action for India’s water security | 24th March, 2026
14 | Policy on reuse of treated wastewater in final stage | 18th Macrh, 2026
15 | Work begins to divert 14 drains flowing into the Ganga and Pandu | 12th March, 2026
16 | STP capacity in the Uttar Pradesh increased tenfold over nine years | 25th March, 2026
17 | West Bengal unveils draft policy on safe reuse of treated wastewater | 10th March, 2026
18 | Namami Gange Extends Support for Yamuna Revival | 26th March, 2026
19 | Team of Experts to Inspect Namami Gange Projects Under ‘Mission Project Completion’ Initiative | 7th March, 2026
20 | Bihar Receives National Recognition on World Water Day 2026 | 24th March, 2026
21 | SRTW Policy Paves the Way for Water Security (https://timesofindia.indiatimes.com/city/lucknow/uttar-pradesh-embarks-on-transformative-path-towards-water-security/articleshow/129786313.cms) | 25th March, 2026
22 | Survey Begins to Stop Drains Flowing into the Ganga and Pandu Rivers in Kanpur | 26th March, 2026
23 | 44 MLD Sewage Treatment Plant to Be Built in Moharda | 6th March, 2026
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Geeta Colony, Pushta 1 Sonia Vihar, ITO Chhath Ghat, Signature Bridge | NGOs- Saksham Bhoomi Fgoundation; Yuva Parivartan Foundation; Friends of Yamuna & Swachh Yamuna Abhiyaan; Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
2 | Workshop on "Restoring and Maintaining the Inter-Relationship of Surface Flow and Sub-Surface (Groundwater) Systems" | Technical Unit , NMCG | 7th March 2026 | Nalanda Hall, Ambedkar International Centre | Ministry , NMCG, CGWB , CWC etc https://x.com/i/status/2030270673780887763
3 | Workshop onConserving Himalayan Glacier | Urban Unit NMCG & NIH | 23rd March 2026 | Hall No 3 , Ambedkar International Centre | Ministry , NMCG, NIH , Wadi Institute , Scientist and Experts https://www.instagram.com/p/DWO-WaaDxtX/?igsh=bjA5N2gwenJsazJ2
4 | Workshop on Sludge Management | Project Unit , NMCG | 23rd March 2026 | Bhim Hall , Ambedkar International Centre | Ministry , NMCG, NWM,Technical Agencies , State Executing & implementing agencies , experts etc https://x.com/i/status/2036324967068180855
UTTARAKHAND
2 | Ganga Swachhta Pakhwada and World Water Day, Uttarakhand | DGCs, academic institutes (Govt. PG/Degree Colleges) & Universities | 16 to 31.03.2026 | Govt. PG/Degree Colleges (Augustmuni, Uttarkashi, Dehradun, Gopeshwar, Joshimath, Jawalapur, Khadi, Ramnagar, Maldevta, Paithani, Lohaghat, Majra Mahadev, Haldwani, Chandrabani, Jahrikhal & Rudraprayag and Phoenics University, Roorkee and Sparsh Himalaya University | College Students, Teachers, Volunteers & Local Communities
3 | National Science Day- Exhibition, Poster Exhibition, Quiz & Competitions, Seminars & Swachhta Sankalp Run (Uttarakhand) | Govt. PG Colleges | 01.03.2026 | Govt. Women College (Haldwani), Govt. PG College (Thalisian) and Omkaranand Saraswati Govt. College, Devprayag | College Students, Teachers & Volunteers
4 | Cleanliness Campaign, Run, Pledge and Guiz & Competitions (Uttarakhand) | Govt. PG Colleges | Entire Month | Govt. PG College (Halwani, Champawat, Thalisain, Pabou, Ramnagar and Haridwar) | College Students, Teachers, Volunteers & Local Communities
UTTAR PRADESH
5 | STP Visit, Meerut, Uttar Pradesh | DGC- Meerut & Schools | 05.03.2026 | STP, Jagriti Vihar | School students & volunteers
6 | Ganga Swachhta Pakhwada and World Water Day, Uttar Pradesh | DGCs, Schools/Colleges, Forest Department, NSS/NCC & NGOs | 16 to 31.03.2026 | Various locations- Schools, Colleges, Ghats and other strategic locations | School/College Students, Teachers, Youth Groups, Volunteers & Local Communities
7 | Hindon Nadi Shodh Yatra, Uttar Pradesh | DGCs | 15 to 19.03.2026 | DGCs- Saharanpur, Shamli, Muzzaffarnagar, Meerut, Baghpat, Ghaziabad & Gautam Budh Nagar | Volunteers & Local Communities
8 | Workshop- Water as a leverage (Prayagraj) | NMCG/SMCG, UN Habitat, Kingdom of Netherlands, Nagar Nigam, DGC- Prayagraj | 19.03.2026 | Kahna Shyam Hotel, Prayagraj | Representatives of partner organisations, Senior Officials and Staff
9 | World Sparrow Day, Jhansi | Forest Department & NGO-Manavta K Liye Ek Kadam- Jhansi | 20.03.2026 | Divisional Forest Office, Forest Range | Volunteers & Local Communities
10 | International Day of Forests, Jhansi | DGC-Jhasi, Forest Department | 21.03.2026 | Forest Range | Volunteers & Local Communities
BIHAR
11 | Jal Mahotsav Pakhwada, Bihar | DGCs | 08 to 22.03.2026 | DGCs- Darbhanga, Buxar, Begusarai, Katihar, Samastipur, Patna, Vaishali, Bhojpur, Madhubani, Jahanabad, Sitamarhi, Sheohar & & Bhagalpur | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
12 | Ganga Swachhta Pakhwada, Bihar | DGCs | 16 to 31.03.2026 | DGCs | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
JHARKHAND
13 | Jal Mahotsav Pakhwada, Chatra, Dhanbad & Ramgarh, Jharkhand | DGC-Chatra, Dhanbadh & Ramgarh | 12.03.2026 | Chatra Block (Chatra); Townhall, Jora Talab, Barkakana, Haribandh, Gola (Ramgarh) and PHED Meeting Hall (Dhanbad) | Volunteers & Local Communities
14 | Ganga Swachhta Pakhwada and World Water Day, Jharkhand | DGCs | 16 to 31.03.2026 | Various Locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
15 | Jal Hai toh Kal Hai- Awareness Rally, Bokaro (Jharkhand) | DGC & District Education Department, Bokaro | 14.03.2026 | Rajkiye UMS, Gomia | School Students, Teachers, Youth Groups, Volunteers & NGOs
16 | Inter School Quiz | DGC- Rajmahal, Jharkhand | 09.03.2026 | Suryadev Ghat, Rajmahal | School Students, Teachers, Youth Groups, & Volunteers
17 | Cleanliness Drives (Industries Based), Bokaro | Dalmia Cement & ONGC, Bokaro | 23.03.2026 | Dalmia Cement Biada & ONGC | Staff, Officials and volunteers
18 | Chaiti Chhath Puja & other regular IEC Activities (Cleanliness Drives, Awareness Rallies, Shapath, Aarti, Quiz & Competitions, Nukkad Natak etc.) | DGCs | Entire Month | Various Locations | School & College Students, Teachers, Youth Groups, Religious groups, Volunteers, NGOs & Local Communities
WEST BENGAL
19 | Outdoor Campaign during 10th International Jangalmahal Utsav & Veshoj Mela, Kolkata | SMCG WB | 22 to 28.03.2026 | Triangular Park (Sarat Chatterjee Park), Gariahat, Kolkata | Local Stakeholders
20 | Jal Mahotsav Pakhwada | DGCs | 08 to 22.03.2026 | DGC- Mrushidabad (Kanchantala Ganga Ghat), Malda (Malda Collge), Hooghly (Stand Road, Chandernagore), North 24 Parganas (Shyamnagar Nanababa Ghat) | School & College Students, Youth Groups, Women Self Help Groups & Local Communities
21 | Ganga Swachhta Pakhwada, West Bengal | DGCs | 16 to 31.03.2026 | Various Locations | School & College Students, Teachers, Youth Groups, Religious groups, Volunteers, NGOs & Local Communities

## MPR 5.5 RCA
(April 2025 - March 2026)
For the month of MARCH
Organisation: River Cities Alliance
Sl. No. | Activity | Till Feb 2026 | 2026-03-26 | Total
1 | Web posts | 64 | 8 | 72
2 | Workshops (excluding 5b /URMP Workshops) | 15 | 2 | 17
3 | Seminar/ Webinar/Meetings | 29 | 2 | 31
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 7 | 0 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 3 | 1 | 4
| b) Others | 19 | 2 | 21
7 | Concept Notes | 8 | 1 | 9
8 | Demands Received
| a) Cities | 11 | 3 | 14
| b) Academia | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) March
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Technical Workshop for Master Plan Preparation in Patna, Bihar | 2 | Patna | 10.03.2026 | 50
2 | Webinar on 'Managing River Health During Large Scale Gatherings - Experiences from Maha Kumbh and Magh Mela' | 3 | Online | 20.03.2026 | 40
3 | Integrated Academic Studio Workshop on Water and River Sensitive Planning for Guwahati | 2 | SPA Bhopal | 20.03.2026 | 35
4 | Webinar on 'Wetland Management for Sustainable Urban Water & River Futures' | 3 | Online | 27.03.2026 | 71
List (Type 1,6) March
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on " Bio-Remediation Facilty of Riyadh, Saudi Arabia" | 1 | 02.03.2026
2 | Inspirational Monday Series on " Singapore Park Connector Network" | 1 | 09.03.2026
3 | Inspirational Monday Series on "Mahadevapura Lake Restoration in Bangalore" | 1 | 16.03.2026
4 | Inspirational Monday Series on "Tamza River Rejuvenation in Azamgarh, Uttar Pradesh under One District, One River Initiative " | 1 | 23.03.2026
5 | Inspirational Monday Series on "South California on Santa Ana River Trail" | 1 | 30.03.2026
6 | Quiz series 5: RCA: Rivers, Cities, and Answers | 1 | 11.03.2026
7 | Quiz series 6: RCA: Rivers, Cities, and Answers | 1 | 18.03.2026
8 | Quiz series 7: RCA: Rivers, Cities, and Answers | 1 | 25.03.2026
9 | City Spotlight No.3: 'Green Bonds for Sustainable Urban Mobility - The case of Pimpri Chinchwad Muncipal Coorporation (PCMC)" | 6b | 25.03.2026
10 | Guidance Note on 'Drone-Based Survey of Rivers for Drainage / Outfalls Mapping and Annotation’ | 6b | 27.03.2026
11 | RCA Newsletter (Q4) | 6a | 30.03.2026
List (Type 7) March
Sl. No. | Subject | Type | Date
1 | Course Outline for "Principles of Urban River Management" - a 4-credit, core course in the School of Environment & Sustainability, Final year, UG students and as a professional elective course in SCET, Surat. | 7 | 29.03.2026
Demands for RCA (Type 8) March
Sl. No. | Subject | Type | Date
1 | Need for technical support and knowledge from Jhansi Municipal Corporation on :- Proliferation of water hyacinth, Undefined river boundaries and Regularize applicable development bye laws as per master plan | 8 | 25.03.2026
2 | Uttarkashi - Request for guidance on religious Solid Waste Management especially Fabrics (Clothes) | 8 | 25.03.2026
3 | Pilibhit - Request for guidance for conducting a survey and study of the city to improve the drainage system / water drainage in Pilibhit | 8 | 25.03.2026

## COE-IT BHU
(April 2025 - March 2026)
For the month of March 2026
Smart Laboratory on Clean Rivers
Sl. No. | Activity | Till Feb-26 | 2026-03-01 | Total
1 | Web posts | 92 | 16 | 108
2 | Workshops / Conference | 7 | 5 | 12
3 | Seminar/ Webinar | 8 | 2 | 10
4 | Exposure Visits | 20 | 1 | 21
5 | URMP Related (Non Ganga Basin) | NA | NA | NA
| a) Meetings in States | NA | NA | NA
| b) Workshops in States | NA | NA | NA
6 | Publications | 0 | 0 | 0
| a) Newsletter | 0 | 0 | 0
| b) Others | 4 | 0 | 4
7 | Consultative Meetings / Interactive Sessions | 29 | 7 | 36
Annexure
List (Type 2,3,5,4)
Sl. No. | Event Topic | Type | Venue | Date/Days/ Duration | Number of Participants
1 | Webinar on Topic: Impact of climate extremes in water catchments and managing treatment to provide safe drinking water | Type 3 | Online | 06.03.2026 | 80
2 | A one-day workshop organized by the National Mission for Clean Ganga (NMCG) under the Ministry of Jal Shakti on the theme:“Restoring the Inter-Relationship of Surface Flow and Sub-Surface (Groundwater) Systems” | Type 2 | New Delhi | 07.03.2026 | 100
3 | A training session on Bhuvan Overview Training was conducted by NRSC (ISRO). The program highlighted Bhuvan’s applications in water and disaster management, along with its APIs, showcasing how geospatial technologies aid informed decision-making and sustainable planning. | Type 2 | Hyderabad | 09.03.2026 - 11.03.2026 | 40
4 | Webinar on Topic: Microplastics Analysis in water using Vibrational Spectroscopy: Navigating ISO/FDIS 16094-2 standards | Type 3 | Online | 12.03.2026 | 25+
5 | Indian Infrastructure Magazine's conference on Solid Waste Management in India & Waste To Energy. | Type 2 | Le Meridien, New Delhi | 12.03.2026-13.03.2026 | 1
6 | National workshop on "Rural water management and Treatment Technologies" | Type 2 | IIT Kanpur | 16.03.2026 - 17.03.2026 | 150
7 | Consultation Workshop on “Effective Municipal Sludge Management in Indian Cities”, organised by the National Mission for Clean Ganga (NMCG) | Type 2 | Dr. Ambedkar International Centre, New Delhi. | 23.03.2026 | 4
8 | Visit to Neela Hauz biodiversity park, Delhi consisting of constructed wetland system was conducted. | Type 4 | New Delhi | 24.03.2026 | 1
List (Type 6)
Sl. No. | Subject | Type | Date
1
2
List (Type 7)
Sl. No. | Consultative Meetings / Interactive Sessions | Type | Venue | Date
1 | Meeting with Centre for science & Environment, New Delhi regarding knowledge sharing for holistic plan and pilot demonstrations in Varuna River basin | Type 7 | New Delhi | 05.03.2026
2 | Meeting with India-EU Water Partnership (IEWP) / GIZ India, regarding bringing on board the international partners in respect of holistic plan and the innovative sustainable technologies for pilot demonstrations in Varuna basin | Type 7 | New Delhi | 06.03.2026
3 | An in-person brainstorming and discussion session at the Ramboll office. Key discussions included improvements to the STP model, integration of the flood model into the DSS framework, and timelines for completing the remaining modules. | Type 7 | Noida | 13.03.2026
4 | Meeting with National Institute of Urban Affairs (NIUA) on knowledge sharing support on holistic plan, pilot demonstrations and discussion on convergence of different plans for rivers. | Type 7 | India Habitat Centre, New Delhi | 16.03.2026
5 | SLCR team visited the DFO, Prayagraj for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Prayagraj | 19.03.2026
6 | Visit to Delhi Jal Board, HQ office was conducted and discussion carried out on decentralised wastewater Treatment plants along with visit to in- house nature based wastewater Treatment facility at DJB premises. | Type 7 | New Delhi | 25.03.2026
7 | Meeting held with Council on Energy, Environment and Water (CEEW) on collaboration on possible areas such as Holistic plan, Smart monitoring, DSS, and Water and wastewater management, Reuse etc. | Type 7 | Online | 27.03.2026