## MPR 1.3_Project under progress
(April 2025 - March 2026)
For the month (As on 10th March 2026)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | COD expected to be declared by 15th March'2026.
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Muzaffarnagar | HAM | 234.03 | 54.5 | 2026-07-01 | COD declared for 22 MLD STP; COD declared for 32.5 MLD STP (Letter dated 12.01.2026, Final CoD start from 01.07.2025 for 15 Years O&M)
9 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
10 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partially COD declared
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date to be declared by 31st Mach 2026. . Pending Conditions precedent include (i) Financial closure; (ii) BEP Approval; (iii) Construction Plan approval; (iv) Phase I design drawing Submission; (v) Escrow Agreement. Site survey, soil investigations, site clearing completed. Site level variations (Actual vs RFP) reported in the review meeting held on 25/02/2026
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | 2025-10-15 | Due to land permission. Land for two STPs is clear for which spearate effective date may be given.

## MPR 1.4_KSDC
April 2025 - March 2026
For the month of February 2026
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | Till January, 2026 | February, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 1 | 2 | 3
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) February 2026
S.No | Event Topic | Type | Venue | Date/Days/ Duration | No. of Participants
1 | Second training program of the Knowledge-cum-Skill Development Centre (KSDC) for Yamuna Task Force at Yamuna Biodiversity Park by the Centre for Environmental Management of Degraded Ecosystems (CEMDE) | 2 | Offline (Yamuna Biodiversity Park) | 16.02.2026- 18.02.2026 | 31
2 | Third Training program of the Knowledge-cum-Skill Development Centre (KSDC) for District Ganga Committees (DGCs) of Uttarakhand at Yamuna Biodiversity Park by the Centre for Environmental | 2 | Offline (Yamuna Biodiversity Park) | 26.02.2026- 28.02.2026 | 12
List (Type 1,6) February
| Sl. No. | Subject |  | Date
List (Type 7) February
| Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of February, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Jan-26 | 2026-02-01
1 | STP Inspection Reports Received **
| Uttrakhand | Apr'25- Jul'2025 | Aug'25 - Nov'25
| Uttar Pradesh | Apr'25- Jul'2025 | Aug'25 - Nov'25
| Bihar | Apr'25- Jul'2025 | Aug'25 - Nov'25
| Jharkhand | Apr'25- Jul'2025 | Aug'25 - Nov'25
| West Bengal | Apr'25- Jul'2025 | Aug'25 - Nov'25
2 | River water Quality Data Received *
| Uttrakhand | Jul'25- Sep'2025 | -
| Uttar Pradesh | Jul'25- Sep'2025 | -
| Bihar | Jul'25- Sep'2025 | -
| Jharkhand | Jul'25- Sep'2025 | -
| West Bengal | Jul'25- Sep'2025 | -
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3726 (Ganga: 1299; Yamuna2427) | 3705 | 3703
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Sep'2025 | -
| Uttar Pradesh | Jan'25- Sep'2025 | -
| Bihar | Jan'25- Sep'2025 | -
| Jharkhand | Jan'25- Sep'2025 | -
| West Bengal | Jan'25- Sep'2025 | -
5 | Number of Publications/Reports | 32 | 5
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB Audit report of SPCBs Laboratory in Ganga States for sampling methodology of bacteriological parameters | 2026-02-27
2 | Status report of Sewage Treatment Plants of Main Stem Ganga basin States (Aug-Nov. 2025) | 2026-02-24
3 | CPCB findings of Jt. Monitoring of STPs of UK and Lab Audit of UKPCB (during 24-27 Nov.2025) | 2026-02-04
4 | CPCB findings of Jt. Monitoring of STPs of UP and Lab Audit of UPPCB (during 15-18 Dec.2025) | 2026-02-03
5 | New Project proposal for Pollution Inventorisation, Assessment & Surveillance (PIAS) and request for continuation of existing PIAS Project | 2026-02-17
Annexure A for S.No 3
| Total GPIs | 3703
| Inspected | 3703
| Complied | 2101 | << Total Action Completed Till date
| Non-Complied | 871 | << Total Action Completed Till date
| Temporary Closed | 371 | << Total Action Completed Till date
| Permanently Closed | 88 | << Total Action Completed Till date

## MPR 3.2_Regulatory Cell
(April 2025 - March 2026)
For the month of Feburary (As on 28th Feb 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of Jan 25 | 11
2 | Application returned back in Feb 26 | 2
3 | Applications decided in Feb 26 | 0
4 | New Applications received in Feb 26 | 4
5 | Pending Application at the end of Feb 26 | 13
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Nov) | 2
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/ Return | Cases Recommended
| 0 | 0 | 0 | 0
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Discharge of Treated Effluent from MDA operated STPs into Chap Salawa Minor under the 220 MLD STP Project, Meerut | Chief Engineer, UP Jal Nigam (Rural) | 2025-10-29 | File with project wing, sought clarification from state
2 | Renewal for 7 years Ram anubhav kendra | Ayodhaya Development Authority | 2025-07-02 | File pending at competant authority for decision

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 28th February 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
Total | 522
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Total: 69
Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (February 2026) Generated on 1st March 2026
Sl. No. | Title | Till 31st January 2026 | 2026-02-01 | Total (as on 1st March 2026)
1 | Total Number Document on GKP | 1345 | 1 | 1346
2 | Other Literature on River | 10000 | 226 | 10226
Ganga
Categories-wise details of documents uploaded between 1st to 28th February 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 1
Books |  | 0
Studies/Reports |  | 0
Guidelines |  | 0
Miscellaneous |  | 0
Ganga River (Main |  | 0
Stem)Water Quality Data
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 0
Total |  | 1
Details of documents uploaded between 1st to 28th February 2026:-
S.No | Category | Subject
1 | Articles | Reducing fecal pollution in small and medium-size cities along the Ganga River

## MPR 5.3-Prayag status
PRAYAG/ Geoportal-MPR February 2026 (Item 5.3, MPR)
(April 2025 - March 2026)
For the month of January (As on 1st Feb 26)
MPR Prayag/GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status*
a | No. of STPs with OCEMS Installed | 280
b | No. of STPs with Flow Data received | 175
c | No. of STPs with Influent Characteristic Data received # | 141
d | No. of STPs with Effluent Characteristic Data received | 186
2 | Data Reliability Status **
a | No. of STPs with Satisfactory Data received | 205
b | No. of STPs with Poor Data Quality (Annex A1) ** | 3
c | No. of STPs with No Data Received (Annex A2) | 75
B | OCEMS based Results communicated to States till Month | Communicated till Jan-2026
C | Eflows report updated till period | Updated till first quarter 2025
D | GDPMS
| No. of Meetings held in January 2026 | 81
| No. of Meetings held in February 2026 | 14
E | Prayag GEO Portal
| No. of Active GIS Layers (Annex B) | 30
| No. of Use Cases | 7

## MPR 5.4-Jan Ganga Vertical_Comm
(April 2025 - March 2026)
For the Month of Febraury 2026 (As on 1st March 2026)
MPR Communication
| Followers | Till Previous Month- January | Current Month- Febraury
1 | Twitter | 122967 | 123184
| Facebook | 510648 | 532515
| Instagram | 122886 | 113293
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 212 post | 30 Videos | 62 mins
| Facebook | 212 post | 48 Videos | 80 mins
| Instagram | 202 post | 31 Videos | 64 Mins
b) | Rebuttals on
| Social Media | 1 Rebuttal on Instagram- | https://www.instagram.com/reel/DUdGLJYjxh_/?igsh=MWkwejEyeTY4amRrMQ==
c) | Positive Stories |  |  | Annex A
| Social Media | 21 Stories | ..\OneDrive\Documents\Desktop\Nadim Personal\MPR, NMCG\MPR\Annexure A_ Feb 2026.docx
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 11 |  | Annex A
|  | Number of Events | Participation
5 | Events Organised by NMCG | Nil |  | Annex B
6 | Events through Partner |  |  | Annex B
a) | DGC | 241 | 517329
b) | NGO
| i). | Cleanliness Drives at Yamuna | Approx. 2000
| ii). | Yamuna Jal Yatra | Approx. 30000
7 | Sponsorship
| Third Party Events |  |  | Annex B
| i). | Envirotech Asia | Approx. 4000
| ii). | Municipalika 2026 | Approx. 10000
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | Pathar Ghat, Kanpur | 2026-02-28 | https://x.com/i/status/2027800104841974005 | https://www.facebook.com/cleanganganmcg/posts/pfbid0gv78CdJGekzyne5xWoUUQRkCsbtXhwvAkqtNHBJcNbR3NnxvqzEyhispS4U5JxW6l | -
2 | Ganga Swachhta, Banaras | 2026-02-28 | https://x.com/cleanganganmcg/status/2027672335109460446?s=20 | https://facebook.com/reel/1964463047839703/ | -
3 | STP status, Phusro Jharkhand | 2026-02-27 | https://x.com/cleanganganmcg/status/2027403658120569301?s=20 | https://x.com/cleanganganmcg/status/2027672335109460446?s=20 | https://www.instagram.com/reel/DVRDlPij7qi/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
4 | Public Review, Haridwar | 2026-02-26 | https://x.com/cleanganganmcg/status/2026967979234140407?s=20 | https://www.facebook.com/reel/1279162124087213 | https://www.instagram.com/reel/DVN9TT3jL08/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
5 | Safe Reuse of Treated Water, UK | 2026-02-26 | https://x.com/cleanganganmcg/status/2026898877618729376?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid024XHwKUXDXsKHSzrEq2n7CG4mFKCismoM8jRgvHZUNfiLfALY64EXoEFmnTnJUaSKl | https://www.instagram.com/p/DVNdrWVDOS3/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
6 | Build India Infra Awards 2026 | 2026-02-25 | https://x.com/i/status/2026640827917770862 | https://www.facebook.com/cleanganganmcg/posts/pfbid02rpmaV5TJ97wTrTuM7HCBVR22Nhw5EYBeLpk2Db9T1AnVZXwQW3Tr6EmmaEQTppd5l | https://www.instagram.com/p/DVLrYeQD2g6/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
7 | Dashesmedh Ghat, Prayagraj | 2026-02-25 | https://x.com/cleanganganmcg/status/2026606083058589854?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02WXvPP8Rv2Y4bKxrXKxDPGNFkAi2FTnkC6DFHfBA5heAx5SK7VLAVQY4sXYU894uRl | https://www.instagram.com/p/DVLYZYSDGiI/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
8 | Public review, Banaras | 2026-02-24 | https://x.com/i/status/2026277037296816525 | https://facebook.com/reel/1840015286699445/ | https://www.instagram.com/reel/DVJCAysjDGA/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
9 | Atal Ghat | 2026-02-23 | https://x.com/i/status/2025892568794546220 | https://www.facebook.com/cleanganganmcg/posts/pfbid02DRJzWKHRvF6wKdqTEVyXfHwDr58AGiaqQiUogRkMW6A8DxkRfG5WXwiJerY9DDmHl | https://www.instagram.com/p/DVGT7h-DGM1/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
10 | Yamuna Clealiness drive, kalindi kunj | 2026-02-22 | https://x.com/i/status/2025544225098781132 | https://www.facebook.com/cleanganganmcg/posts/pfbid0Ya633dxDxMSQbjHr7jCUj3qH6GM3T3FKWuDpZ65wdhJ1RSq3EHgtkjAXYPe1fbfil | https://www.instagram.com/p/DVD16hYj8xJ/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
11 | Sarsaiya Ghat, Kanpur | 2026-02-21 | https://www.facebook.com/cleanganganmcg/posts/pfbid02iVqoit1ttUJ4w1TpV3PSJG2jEzMmAyDJ3y7MhuBGBuYAXjejtgLGEDDBQEsacsxMl | https://www.facebook.com/cleanganganmcg/posts/pfbid02iVqoit1ttUJ4w1TpV3PSJG2jEzMmAyDJ3y7MhuBGBuYAXjejtgLGEDDBQEsacsxMl | https://www.instagram.com/p/DU5VJkODNfU/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
12 | Banaras STPs | 2026-02-21 | https://x.com/i/status/2025086000209559944 | https://fb.watch/FAXn5kdHdX/ | https://www.instagram.com/reel/DVAlOvbj3Zd/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
13 | Public review, Banaras | 2026-02-20 | https://x.com/i/status/2024831406481035373 | https://fb.watch/FAX9x8lbsb/ | https://www.instagram.com/reel/DU-wt2wjcQu/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
14 | Atal Ghat Video | 2026-02-19 | https://x.com/i/status/2024444932694691878 | https://fb.watch/FAXvhlA6f9/ | https://www.instagram.com/reel/DU8CVX_j2iN/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
15 | NMCG STPs project updates | 2026-02-16 | https://x.com/i/status/2023334349471731769 | https://www.facebook.com/cleanganganmcg/posts/pfbid037okhTht1B9FfzLcZ7Crj4i1nPyf1H2kUAQwN3vQd7hPtEi6z3SvDVCCwiogW2vgAl | https://www.instagram.com/p/DU0KBQFjDTH/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
16 | Gangetic Dolphin sighted, Hoogly | 2026-02-16 | https://x.com/i/status/2023331571739283664 | https://www.facebook.com/cleanganganmcg/posts/pfbid0UGKka8semvDv2rzxzY6cD4oYRSCxB9iGhokCR9Swg2GDriNx8UQSRFCc5HEH1GXDl | -
17 | STP updated, Vrindavan | 2026-02-14 | https://x.com/i/status/2022579458956538321 | https://www.facebook.com/cleanganganmcg/posts/pfbid02ouGvNY75JykbSsReRhPBR5bDBPAD4P6Z9sWJwxK5yzFPZ7WLKcEcgh5wXQoGJH1ml | https://www.instagram.com/p/DUuxEufD-hG/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
18 | Reviving Tamsa River | 2026-02-14 | https://x.com/i/status/2022709260183048303 | https://www.facebook.com/cleanganganmcg/posts/pfbid0DfcogrQy89zdSkAN15BEcLYay4S1x7mfYPd8hK9W5r723qAoRePMjrMfCNeHYRQZl | https://www.instagram.com/p/DUvtgbwDyBE/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
19 | Jajmau CETP | 2026-02-11 | https://x.com/i/status/2021578945347608784 | https://www.facebook.com/cleanganganmcg/posts/pfbid0XBGjmfSzxmCvq39MbP4i9cjcDdLGzBDYkZH6vuGDedowGPc7SXaVTtWg4qLqr3NJl | https://www.instagram.com/p/DUnqS7ej6nZ/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
20 | Public review, Prayagraj | 2026-02-11 | https://x.com/i/status/2021132032261136868 | https://www.facebook.com/reel/1525046968560413 | https://www.instagram.com/reel/DUkeYnJgKrw/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
21 | Public review (Fisherman) | 2026-02-10 | https://x.com/i/status/2021078632790417577 | https://fb.watch/FAYwSmYX59 | -
22 | Namami Gange Mission gives new momentum to Ganga conservation in Uttarakhand | 24th Feb, 2026
23 | Cleaner Hooghly water boosts Gangetic dolphin sightings | 10th Feb, 2026
24 | Preparations to start the STP before the deadline gather pace | 20th Feb, 2026
25 | 274.31 crore STP to curb Ganga–Varuna pollution | 21st Feb, 2026
26 | 56.88 crore to develop the origin site; Gomti to get a new lease of life | 01st Feb, 2026
27 | Bihar’s biggest STP to come up; dirty water will no longer flow into the Ganga | 19th Feb, 2026
28 | NMCG team from Delhi reviews the condition of rivers | 13th Feb, 2026
29 | A 100 MLD STP will reduce pollution in the Yamuna | 20th Feb, 2026
30 | A strong push to make the Ganga cleaner through technology | 21st Feb, 2026
31 | Three STPs to be built at three locations at a cost of ₹127 crore | 16th Feb, 2026
32 | Nana Rao Ghat: A remarkable confluence of history, faith, and development | 24th Feb, 2026
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Envirotech Asia | Radeecal Communications & NMCG | 04 to 06.02.2026 | CIDCO Exhibition & Convention Centre, Navi Mumbai, Maharashtra | Municipal Corporations, environment professionals, experts & leaders
2 | Municipalika (Namami Gange Exhibition & Session) | India Trade Promotion Organisation (ITPO) & NMCG | 25 to 27.02.2026 | Bharat Mandapam, Delhi | Central & State Government, Diplomats, Global Leaders, Municipal Bodies, ULBs, Planners & Experts
3 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Sonia Vihar Zero Pushta, Shamshaan Ghat Geeta Colony, Yamuneshwar Ghat Wazirabad, Kalindi Kunj Ghat | Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
4 | Yamuna Jal Yatra | Parmarth Samaj Sevi Sanstha & NMCG | 29.01.26 to 26.02.26 | Uttar Pradesh, Haryana & Delhi | Jal Saheli's, Gram Panchayat, NGOs
5 | Swachta Abhiyan | GGIC Jwalapur Haridwar | 2026-02-07 | Haridwar Rishikesh | College Students, Teachers, Volunteers & Local Communities
6 | Ganga Run & Rangoli Competition | Bal Ganga Sendul Kema | 2026-02-11 | Baal Ganga Sendu Kemar Tehri Garhwal | College Students, Teachers, Volunteers & Local Communities
7 | Ganga Awareness and Aarti Workshop | SMCG Uttarakhand | 15 to 19.02.2026 | Parmarth Niketan Rishikesh | Religious Groups, Youth Groups, Volunteers & Local Communities
8 | Awareness & Sustainability Programme | Graphic Era Hill University | 18 to 19.02.2026 | Prof. K.P. Nautiyal Auditorium, Dehradun | College Students, Teachers, Volunteers & Local Communities
9 | World Wetland Day- Bird Festival & Visits to Wetlands (Activities- Field Visits, Quiz & Competitions), Uttar Pradesh | SMCG/DGC, Forest Departments, Schools & Colleges, Youth Groups | 02 to 08.02.2026 | DGC- Jhansi (Simradha Dam Tal, Pahuj River), Dr. Ambdekarnagar (Bhaduna Tal Katehari), Maharajganj (Malav and Suadhi Tal), Meerut, Hastinapur (Bhikund Wetland), Auraiya (Jamuha Wetland & Vedic Inter College) & Muzzaffarnagar (Haiderpur Wetland) | School/College Students, Teachers, Youth Groups & Volunteers
10 | Science Exhibition, Jhansi, Uttar Pradesh | DGC-Jhansi & Little Life Public School | 10.02.2026 | Little Life Public School | School students, teachers & volunteers
11 | Cleanliness drives, awareness rallies, competitions, chaupal, aarti & swachhta shapath (Bihar) | DGC- Darbhanga, Katihar, Samastipur, Jahanabad, Siwan, Madhubani, Bhojpur, | Entire Month | Katihar (Karhagola Ghat, Manihari Ganga Ghat), Darbhanga (Bagmati River Ghat, Kabibpur Pond Ghat), Samastipur (Rasulpur Sidhi Ghat), Bhojpur (Mahuli Ganga Ghat Chakwat Talab), Jahanabad (Sangam Ghat), Siwan (Shivvarat Sah Ghat, Daha River) Madhubani (Nagar Panchayat Benipatti, Bada Bazar, Madhubani) | College Students, Teachers, Religious Groups, Volunteers & Local Communities
12 | Wetland Day (Bihar) | DGC- Vaishali & Sheohar | 02.02.2026 | Vaishali (Konhara Ghat, Hajipur) | School students, teachers & volunteers
13 | Wetland Day (Cleanliness drives, competitions- slogan writing, drawing, painting, awareness rallies) & regular yoga sessions and aarti (Jharkhand) | DGC & Nagar Parishad/ Nagar Panchayat- Rajmahal, Sahibganj, Chatra (District Education Department), Ramgarh (District Education Dept. & IIT-ISM) | 02.02.2026 | Sahibganj (Mukteshwar Dham Ghat), Chahtra (various schools), Ramgarh (Gandhi Memorial), Rajmahal (Surya Narayan Ghat) | College students, teachers, religious groups, youth groups, volunteers & local communities
14 | World Wildlife Day (Seminar, workshops & poster making) (Jharkhand) | DGC- Bokaro, Dhanbad | 02.02.2026 | various colleges | College students, teachers & volunteers
15 | Rajkiye Itkhori Mahotsav (Jharkhand) | DGC- Chhatra | 19.02.2026 | Itkhori, Mahane Nadi Ghat | Local Communities
16 | Maghi Mela (Jharkhand) | DGC & Tourism Department | 01 to 04.02.2026 | Rajmahal (Surya Narayan Ghat) | Local Communities
17 | Educational Visit | DGC- Howrah | 16.02.2026 | STP Project Site, Howrah | College students, teachers and volunteers
18 | Creative activity, Competitions & Sports Activities (Competitions, Run, Marathon, Cycling) | DGC- North 24 Parganas & Hooghly | 01 & 02.02.2026 and 21st & 22.02.2026 | Kantapokar Sports Academy, Bhatpara; Lenin Ground, Volleyball Ground, Gosthgopal Indoor Maidan, B.K.C High School Ground, Hooghly | School/ College students, teachers, youth groups & volunteers
19 | Nukkad Natak/ Street Plays | SMCG & DGC- Malda, North 24 Parganas | Entire Month | Schools, Markets, Local Streets, Ghats & other important locations | Youth groups, stakeholders, partners, NGOs and volunteers
20 | Exhibition (Education Fair, Mini Kumbh Mela, 49th International Book Fair) | SMCG & DGC- Hooghly | 28.01.2026 to 14.02.2026 | Hooghly (HIT Campus & Saptrishi Ganga Ghat), Saltlake (Kolkata) | Students, teachers & volunteers

## MPR 5.5 RCA
(April 2025 - March 2026)
For the month of FEBRUARY 2026
Organisation: River Cities Alliance
Sl. No. | Activity | Till Jan 2026 | 2026-02-26 | Total
1 | Web posts | 56 | 8 | 64
2 | Workshops (excluding 5b /URMP Workshops) | 13 | 2 | 15
3 | Seminar/ Webinar/Meetings | 28 | 1 | 29
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 6 | 1 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 3 | 0 | 3
| b) Others | 12 | 6 | 18
7 | Concept Notes | 8 | 0 | 8
Annexures
List (Type 2,3,4,5) December
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Faculty Development Programme (FDP) on Water and River Sensitive Urban Development | 2 | IIT-Roorkee | 05.02.2026 - 06.02.2026 | 25
2 | Webinar on ' Municipal Green Bonds - The case of Pimpri Chinchwad Municipal Coorporation' | 3 | Online | 13.02.2026 | 65
3 | Student Thesis Competition in Reimaging Urban Riveras 6.0 Writeshop | 2 | India Habitat Centre | 26.02.2026 - 28.02.2026 | 20
4 | Meeting with Secretary Urban Development, Puducherry | 5a | Puducherry | 01.02.2026 | 7
List (Type 1,6) December
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on " Wetland Restoration - A Case Study of Bashettihalli Wetland in Bengaluru" | 1 | 02.02.2026
2 | Inspirational Monday Series on " Community driven Lake Rejuvenation - A Case Study of Bathlapalli Lake in Chennai by United Way " | 1 | 09.02.2026
3 | Inspirational Monday Series on "Rejuvenation of degraded lakes using Nature Based Solutions - A Case Study of Neela Hauz Khas Lake in Delhi" | 1 | 16.02.2026
4 | Inspirational Monday Series on "Restoration of degraded lakes - A Case Study of Tigaria Badshah Lake in Indore" | 1 | 23.02.2026
5 | Quiz series 1 : RCA: Rivers, Cities, and Answers | 1 | 04.02.2026
6 | Quiz series 2: RCA: Rivers, Cities, and Answers | 1 | 11.02.2026
7 | City Spotlight No.2: 'Urban Flood Management Cell of Gorakhpur' | 6b | 12.02.2026
8 | Quiz series 3: RCA: Rivers, Cities, and Answers | 1 | 18.02.2026
9 | Quiz series 4: RCA: Rivers, Cities, and Answers | 1 | 25.02.2026
10 | River Sensitive Master Plans - Recommendations for Draft Development Plan 2031 of Dehradun | 6b | 11.02.2026
11 | River Sensitive Master Plans - Recommendations for Draft Development Plan 2035 of Surat | 6b | 13.02.2026
12 | River Sensitive Master Plans - Recommendations for Draft Development Plan 2031 of Vadodara | 6b | 13.02.2026
13 | Guidelines for Integrating River Sensitivity into Master Plans” - a checklist for Urban Development and Planning Agency (Draft) | 6b | 18.02.2026
14 | Student Thesis Competition 6.0 Product (Draft) - 'Making Water Visible: Interpretative & Signage Toolbox for Urban River Ecosystems in India' | 6b | 27.02.2026
List (Type 7) December
Sl. No. | Subject | Type | Date

## COE-IT BHU
(April 2025 - March 2026)
For the month of February
Smart Laboratory on Clean Rivers
Sl. No. | Activity | Till January-26 | 2026-02-01 | Total
1 | Web posts | 88 | 4 | 92
2 | Workshops / Conference | 6 | 1 | 7
3 | Seminar/ Webinar | 7 | 1 | 8
4 | Exposure Visits | 18 | 2 | 20
5 | URMP Related (Non Ganga Basin) | NA | NA | NA
| a) Meetings in States | NA | NA | NA
| b) Workshops in States | NA | NA | NA
6 | Publications | 0 | 0 | 0
| a) Newsletter | 0 | 0 | 0
| b) Others | 4 | 0 | 4
7 | Consultative Meetings / Interactive Sessions | 23 | 6 | 29
Annexure
List (Type 2,3,5,4)
Sl. No. | Event Topic | Type | Venue | Date/Days/Duration | Number of Participants
1 | SLCR team visited STP regarding its performance evaluation including (1 RA, and 2 Assistant professor) | Type 4 | Bingawan, Kanpur | 14.02.2026 | 3
2 | SLCR team visited STP regarding its performance evaluation including (1 RA, and 2 Assistant professor) | Type 4 | Jajmau, Kanpur | 14.02.2026 | 3
3 | SLCR participated in Workshop on “Proposal for Institutional Reforms in Urban Water Sector - Moving towards Drink from Tap” | Type 2 | Civil Services Officers Institute (CSOI), K.G. Marg , New Delhi | 17.02.2026 | 25+
4 | Transient Electromagnetics (TEM): Applications in Hydrogeological Investigations for Mining and Groundwater Resources | Type 3 | Online | 25.02.2026 | 1
List (Type 6)
Sl. No. | Subject | Type | Date
1
2
List (Type 7)
Sl. No. | Consultative Meetings / Interactive Sessions | Type | Venue | Date
1 | SLCR team visited the BDO, Phoolpur, Prayagraj for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Prayagraj | 04.02.2026
2 | SLCR team visited the DFO, Bhadohi for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Bhadohi | 13.02.2026
3 | Meeting with Assistant District Panchayat Raj Officer (ADPRO) for follow up of permission letters for the field demonstration | Type 7 | Vikas Bhawan, Varanasi | 20.02.2026
4 | A meeting was held to review the ongoing Decision Support System modules and MAR strategy being developed by IIT (BHU). Dr. Nikhilesh and Dr. Akash from IIT (BHU) participated in the meeting. | Type 7 | UP Ground Water Department, Lucknow | 20.02.2026
5 | An online presentation on non-target screening of water by Prof. Jan H. Christensen, and a presentation on chemicals of emerging concern: Workflow, by Ph.D Scholar Thomas Karlsson from the University of Copenhagen, Denmark | Type 7 | Online | 23.02.2026
6 | SLCR participated in the meeting with IITs/IISc and Session In-charge of the Country Forum (CF) to finalise list of potential participating country during 9th India International Water Week-2026 | Type 7 | Online | 25.02.2026