## MPR 1.3_Project under progress
(April 2025 - March 2026)
For the month (As on 1 Feb 26)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
4 | I&D and STP at Khankharbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | Power connection provided on 10th December 2025. STP under Trial and COD expected to be declared by 15th March'2026.
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Muzaffarnagar | HAM | 234.03 | 54.5 |  | COD declared for 22 MLD STP; Partial COD declared for 32.5 MLD STP due to pending work on IPS 2A. The IPS 2A work has been completed. Full COD declaration documentation under review at UPJN.
9 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
10 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partially COD declared
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date to be declared by 3rd week of Jan'26. Pending Conditions precedent include (i) Financial closure; (ii) BEP Approval; (iii) Construction Plan approval; (iv) Phase I design drawing Submission; (v) Escrow Agreement. Financial closure documents received and under examination. Site survey, soil investigations, site clearing completed.
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | 2025-10-15 | Due to land permission. Land for two STPs is clear for which spearate effective date may be given.

## MPR 1.4_KSDC
(April 2025 - March 2026)
For the month of January
Organisation: Knowledge-cum-Skill Development Centre (KSDC)
Sl. No. | Activity | Till December 25 | 2025-01-01 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 1 | 0 | 1
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) January
Sl. No. | Event Topic | Type | Venue | Number of Participants | Date/Days /Duration
11.09.2025 to 13 .09.2025
List (Type 1,6) January
Sl. No. | Subject |  | Date
List (Type 7) January
Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of January, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Dec-25 | 2026-01-01
1 | STP Inspection Reports Received **
| Uttrakhand | Apr'25- Jul'2025 | -
| Uttar Pradesh | Apr'25- Jul'2025 | -
| Bihar | Apr'25- Jul'2025 | -
| Jharkhand | Apr'25- Jul'2025 | -
| West Bengal | Apr'25- Jul'2025 | -
2 | River water Quality Data Received *
| Uttrakhand | Jul'25- Sep'2025 | -
| Uttar Pradesh | Jul'25- Sep'2025 | -
| Bihar | Jul'25- Sep'2025 | -
| Jharkhand | Jul'25- Sep'2025 | -
| West Bengal | Jul'25- Sep'2025 | -
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3726 (Ganga: 1299; Yamuna2427) | 3681 | 3705
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Jun'2025 | Jan'25- Sep'2025
| Uttar Pradesh | Jan'25- Jun'2025 | Jan'25- Sep'2025
| Bihar | Jan'25- Jun'2025 | Jan'25- Sep'2025
| Jharkhand | Jan'25- Jun'2025 | Jan'25- Sep'2025
| West Bengal | Jan'25- Jun'2025 | Jan'25- Sep'2025
5 | Number of Publications/Reports | 28 | 4
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB letter to 'The Principal Secretary, Urban Development and Housing Department, Govt of Bihar' For necessary Actions on Solid Waste Dumping in Drains Discharging in River ganga in Bihar (by email) | 2026-01-22
2 | CPCB brief Report of 37 STPs of River Yamuna monitoring (Aug-Nov'2025) and informing that STPs monitoring in Yamuna has been stopped after Nov'2025. (by email) | 2026-01-23
3 | CPCB Report of 52 Yamuna Drains monitoring (May-Nov'2025) | 2026-01-21
| CPCB Letter to UP and UK for Delay in upload of Manual Water Quality Monitoring Data of River ganga on Environmental Water Quality Data Entry Systems (EWQDES) | 2026-01-14
Annexure A for S.No 3
| Total GPIs | 3726
| Inspected | 3705
| Complied | 2127
| Non-Complied | 664
| Temporary Closed | 348
| Permanently Closed | 74

## MPR 3.2_Regulatory Cell
(April 2025 - March 2026)
For the month of January (As on 31st Jan 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of Dec 25 | 10
2 | Application returned back in Jan 26 | 5
3 | Applications decided in Jan 26 | 1
4 | New Applications received in Jan 26 | 7
5 | Pending Application at the end of Jan 26 | 11
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Oct) | 2
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/ Return | Cases Recommended
2025-12-29 | 13 | 4 | 3 | 1
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Discharge of Treated Effluent from MDA operated STPs into Chap Salawa Minor under the 220 MLD STP Project, Meerut | Chief Engineer, UP Jal Nigam (Rural) | 2025-10-29 | File with project wing, sought clarification from state
2 | Renewal for 7 years Ram anubhav kendra | Ayodhaya Development Authority | 2025-07-02 | File pending at competant authority for decision

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
Total | 521
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Total: 69

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (January 2026)
Generated on 1st February 2026
Sl. No. | Title | Till 31th December 2025 | 2026-01-01 | Total (as on 1st February 2026)
1 | Total Number Document on GKP | 1315 | 30 | 1345
2 | Other Literature on River Ganga | 10000 | 0 | 10000
Categories-wise details of documents uploaded between 1st to 31st January 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 0
Studies/Reports |  | 1
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 14
Coffee Table Books |  | 0
River Series |  | 15
Total |  | 30
Details of documents uploaded between 1st to 31st January 2026:-
S.No | Category | Subject
1 | Water Quality Data | Uttarakhand Stretch (FS)
2 | Water Quality Data | West Bengal Stretch (FS)
3 | Water Quality Data | West Bengal Stretch (FS)
4 | Water Quality Data | Uttar Pradesh Stretch (FS)
5 | Water Quality Data | Uttar Pradesh Stretch (FS)
6 | Water Quality Data | Jharkhand Stretch (FS)
7 | Water Quality Data | Jharkhand Stretch (FS)
8 | Water Quality Data | Bihar Stretch (FS)
9 | Water Quality Data | Bihar Stretch (FS)
10 | Water Quality Data | West Bengal Stretch (FC)
11 | Water Quality Data | Uttar Pradesh Stretch (FC)
12 | Water Quality Data | Jharkhand Stretch (FC)
13 | Water Quality Data | Bihar Stretch (FC)
14 | Water Quality Data | Bihar Stretch (FC)
15 | River Series | Tamas river
16 | River Series | Sarju river
17 | River Series | Pindar river
18 | River Series | Pahuj river
19 | River Series | North Koel river
20 | River Series | Newaj river
21 | River Series | Kuwano river
22 | River Series | Hindon river
23 | River Series | Gambhir river
24 | River Series | Dhasan river
25 | River Series | Chhoti Gandak river
26 | River Series | Burhi Gandak river
27 | River Series | Belan river
28 | River Series | Banganga river
29 | River Series | Banas river
30 | Reports | ECOLOGICAL INVENTORY OF YAMUNA RIVER IN NCT DELHI

## MPR 5.3-Prayag status
(April 2025 - March 2026)
For the month of January (As on 1st Feb 26)
MPR Prayag/GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status*
a | No. of STPs with OCEMS Installed | 278
b | No. of STPs with Flow Data received | 183
c | No. of STPs with Influent Characteristic Data received # | 131
d | No. of STPs with Effluent Characteristic Data received | 195
2 | Data Reliability Status **
a | No. of STPs with Satisfactory Data received | 201
b | No. of STPs with Poor Data Quality (Annex A1) ** | 4
c | No. of STPs with No Data Received (Annex A2) | 77
B | OCEMS based Results communicated to States till Month | Communicated till Jan-2026
C | Eflows report updated till period | Updated till first quarter 2025
D | GDPMS
| No. of Meetings held in November 2025 | 75
| No. of Meetings held in December 2025 | 21
E | Prayag GEO Portal
| No. of Active GIS Layers (Annex B) | 30
| No. of Use Cases | 7
PRAYAG/ Geoportal-MPR January 2026 (Item 5.3, MPR)

## MPR 5.4-Jan Ganga Vertical_Comm
(April 2025 - March 2026)
For the Month of January 2026 (As on 1st February. 26)
MPR Communication
| Followers | Current Month (December) | Current Month (Janauary)
1 | Twitter | 123064 | 122967
| Facebook | 491051 | 510648
| Instagram | 99.8K | 112886
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 220 post | 51 Videos | 108 mins
| Facebook | 220 post | 51 Videos | 108 mins
| Instagram | 220post | 50 Videos | 105 Mins
b) | Rebuttals on
| Social Media | 5
c) | Positive Stories | 12 Stories |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 12 |  | Annex A
|  | Number of Events | Participation
5 | Events Organised by NMCG |  |  | Annex B
| Jal Evam Swachhta Prahari Samvad | 1 | 600
6 | Events through Partner |  |  | Annex B
a) | DGC | Approx. 204 | Approx. 1,51,147
b) | NGO | 4- Cleanliness Drives on Yamuna | Approx. 2000
c) | Institutes
| i). | Inaugural Event- Aquatic Biodiversity Conservation Initiatives (NMCG & WII- organised Jointly) | Approx. 700
| ii). | 15- Regular Activities ( Uttarakhand) | Approx. 500
7 | Sponsorship
Third Party Events
| i). | Saksham Bhoomi | Approx. 500 | Annex B
| ii). | Yamuna Jal Yatra | Approx. 700
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | Public Review | 2026-01-31 | https://x.com/i/status/2017620036685603285 | https://fb.watch/E--8fCEQhN/ | https://www.instagram.com/reel/DULhk00D5Dt/?igsh=MWJrYmhkY3UwMWFsNQ==
2 | Public Review | 2026-01-30 | https://x.com/i/status/2017090944294859207 | https://fb.watch/E--nxMch1H/ | https://www.instagram.com/reel/DUHw0L7j_mp/?igsh=em40MnU0cXZzcjU0
3 | Public Review | 2026-01-29 | https://x.com/i/status/2016523189220934003 | https://fb.watch/E--vElHJcE/ | https://www.instagram.com/reel/DUDu3mUD3l5/?igsh=MXhnNWZmYTl3aDIyaw==
4 | STP updates | 2026-01-27 | https://x.com/i/status/2016098395006632280 | https://www.facebook.com/cleanganganmcg/posts/pfbid028LRkQBC7RC7r3Dm1Jx6J5iDmzgxEPA6GqvdBVMEaQMuJ7cwifMsQ83gJ4T6rWguol | https://www.instagram.com/p/DUAuXGMjxaW/?igsh=MW8wa2NpcXBjcGVjdw==
5 | Ganga Prahari | 2026-01-25 | https://x.com/i/status/2015385312827187405 | https://www.facebook.com/cleanganganmcg/posts/pfbid02PZHLRn7JCBcfUP2fEYMF4Labdgr1M4MBpfV6GoxTkvd6tC2Zis52HHdAkzecEiSQl | https://www.instagram.com/p/DT7pqhZj8DP/?igsh=MWlzeWthbzc1aXNpOA==
6 | Yamuna Cleanliness Drive | 2026-01-25 | https://x.com/i/status/2015387760606208311 | https://www.facebook.com/cleanganganmcg/posts/pfbid02ktdeAmcinMD87A54tNA7u6HbgcySAUoM2cWXTk5y5toGutbAv8xvnmQXVjfcML4yl | https://www.instagram.com/p/DT7yFWQD1DK/?igsh=MXA3NDRhbHJzcDlyNA==
7 | Kukrail Centre Story | 2026-01-21 | https://x.com/i/status/2013621816716325060 | https://fb.watch/F00j8MHWOB/ | https://www.instagram.com/reel/DTvLRwhDFmL/?igsh=Ym4zbWhkdXJld2l2
8 | STP Story Phusro | 2026-01-21 | https://x.com/i/status/2013492040282304883 | https://fb.watch/F00wRECWWb/ | https://www.instagram.com/reel/DTuMbOvjLc0/?igsh=NnpsZXAxc2t3MG54
9 | Turle Story | 2026-01-20 | https://x.com/i/status/2013126915134202227 | https://fb.watch/F00EDkw-5M/ | ------------------------------------
10 | Public Review | 2026-01-20 | https://x.com/i/status/2012055462402015527 | https://www.facebook.com/reel/1413709853490485 | https://www.instagram.com/reel/DTj_UeUDLeU/?igsh=NWE5aThtcjZsbHd2
11 | Fish Ranching | 2026-01-16 | https://x.com/i/status/2011695686002360661 | https://www.facebook.com/cleanganganmcg/posts/pfbid02t4HaZMn3zjatGKJgfCx1zvAEaWgcad6N7X2qbMpaj8Y7zh2xRwoazWSkFA15w1wAl | https://www.instagram.com/p/DThYRryjLcV/?igsh=bmthaDY3ZmozbjFy
12 | STP Status Updates | 2026-01-13 | https://x.com/i/status/2010611720952365227 | https://www.facebook.com/cleanganganmcg/posts/pfbid02AWnRju4TNvjvVZyHWf6Hb39bjxKnPBEbWNM5qcn5r2sFYfgSQQgYw3p6N1NMvd6fl | https://www.instagram.com/p/DTZve36DLmo/?igsh=dXAwaXBvb3lyc3Zz
13 | Rebuttals | 2026-01-12 | 1. https://x.com/cleanganganmcg/status/2010645139593769004?s=20
14 | Rebuttals | 2026-01-12 | 4. https://x.com/cleanganganmcg/status/2010689450221961550?s=20
15 | Rebuttals | 2026-01-14 | 5. https://x.com/cleanganganmcg/status/2011377186801103252?s=20
16 | Rebuttals | 2026-01-28 | 2. https://x.com/cleanganganmcg/status/2016459590788055401?s=20
17 | Rebuttals | 2026-01-20 | 3. https://x.com/cleanganganmcg/status/2013575855734448419?s=20
18 | Namami Gange Mission Gains Momentum in West Bengal with Two Major Sewerage Projects Going Live | 14th Jan, 2026
19 | Namami Gange project completion in Q3 | 11th Jan, 2026
20 | Shuklaganj, Unnao STP Trial Operations Begin | 7th Jan, 2026
21 | Drain Mapping to Strengthen Monitoring of Ganga Pollution | 13th Jan, 2026
22 | STP plant operational in Bhagalpur | 25th Jan, 2026
23 | Two Monitoring Stations Planned to Ensure Adequate Water Flow in Yamuna | 15th Jan, 2026
24 | Namami Gange Team Conducts Detailed Survey of Tilokhar River Origin | 16th Jan, 2026
25 | Two New STPs Proposed to Clean Yamuna River in Prayagraj | 21st Jan, 2026
26 | Support to maintain E-flow in the Yamuna in Haryana and Uttar Pradesh | 24th Jan, 2026
27 | A River Is a Lifeline, Not Just a Water Channel”: Union Jal Shakti Minister Shri C.R. Paatil | 14th Jan, 2026
28 | Japanese ‘Johkasou Technology to Curb Ganga Pollution, New STP Planned | 23th Jan, 2026
29 | Ganga flows uninterrupted in Kashi as new STPs are built and old ones upgraded | 9th Jan, 2026
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Jal Evam Swachhta Prahari Samvad | NMCG | 27.01.2026 | PSOI, Chanakyapuri, Delhi | Ganga Prahari, Swachhta Prahari, DPOs, NGOs, Volunteers, Yamuna Task Force etc.
2 | Inaugural Event- Aquatic Biodiversity Conservation Initiatives | (NMCG & WII- Conducted Jointly) | 13.01.2026 | WII Campus, Dehradun | Students, Volunteers, Partner organisations
3 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | ITO Chhath Ghat, Sonia Vihar 2.5 Pushta, Soor Ghat and Geeta Colony Ghat | Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
4 | Yamuna Samagam | Saksham Bhoomi & NMCG | 16.01.2026 | Bal Bharati School, Delhi | School Students, Teachers, Doctors, volunteers, & NGOs
5 | Yamuna Jal Yatra | Parmarth Samaj Sevi Sanstha & NMCG | 29.01.26 to 26.02.26 | Uttar Pradesh, Haryana & Delhi | Jal Saheli's, Gram Panchayat, NGOs
6 | Regular Awareness Activities, Workshops, Cleanliness Drives, Painting Competitions, & Signature Campaigns- (Mag Mela, Makar Sankranti & Maghotsav) | Govt. PG Colleges- GGIC Jawalapur Haridwar, Lohaghat, Champawat, Uttarkashi, Augustyamuni, Gopeshwar, Maldevta, Ramnagar, Haldwani & Almora (Uttarakhand) | Entire Month | Govt. PG Colleges- GGIC Jawalapur Haridwar, Lohaghat, Champawat, Uttarkashi, Augustyamuni, Gopeshwar, Maldevta, Ramnagar, Haldwani & Almora | College Students, Teachers, Volunteers & Local Communities
7 | Dolphin Conservation Awareness Programme | DGC- Chandauli (Uttar Pradesh) | 20.01.2026 | Krishna Public School & BNS Public English School, Dulhipur, Chaundauli | College Students, Teachers, Volunteers & Local Volunteers
8 | Maha Ganga Aarti | DGC- Bhojpur, Vaishali & Buxar (Bihar) | 01.01.2026 | Mahauli Ganga Ghat (Bhojpur), Konhara Ghat (Vaishali) & Nath Baba Ghat (Buxar) | Religious Groups, Youth Groups, Volunteers & Local Communities
9 | Cleanliness Drives, Ganga Gallery, Ganga Aarti on Ghats, Drawing & Essay Competitions, Plantation in schools- on the occasion of Patang Mahotsav, Makar Sankranti & Republic Day | DGC- Dhanbad, Sahibganj (Jharkhand) | Entire Month | Maithon Dam & Panchet (Dhanbad), various schools, Ghats & other strategic locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
10 | Shabdh Sarita Mahotsav (Book Fair) | DGC- Bokaro, Sahibganj, Chatra & Ramgarh (Jharkhand) | 07.01.26 & 08.01.26 | Shibu Soren Smriti Bhawan, Town Hall Bokaro | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
11 | Ganga Sagar Mela | DGC- South 24 Parganas | 11 to 17.01.2026 | Ganga Sagar Mela Ground, Sagar Block, South 24 Parganas | Youth Groups & Local Communities
12 | Namami Gange Exhibition- (During KMDA Flower Show & 49th International Kolkata Book Fair) | SMCG- West Bengal | 21 to 25.01.2026 & 22 to 27.01.2026 | Flower Show at Rabindra Sarobar & Book Fair at Saltlake | Youth Groups & Local Communities
13 | Street Plays for Behavioural Change Communication | DGC- Murshidabad, Malda & North 24 Parganas | Entire Month | Various schools | Students, Teachers & Volunteers
14 | Creative Activities & Competitions | DGC- North 24 Parganas | 23 to 25.01.2026 | Deb Narayan High School, Hingalganj Block, North 24 Parganas | Students, Teachers & Volunteers
15 | Installation of Permanent Hoardings | DGC- Hooghly | Entire Month | Tribeni Cremation Ganga Ghat, Bansberia Municipal Area & Hangseswari Mandir | Youth & Religious Groups, Volunteers & Local Communities
16 | Grafiti | DGC- Purba Medinipur, Purba Bardhaman, Howrah | Entire Month | Ghats & other strategic locations | Youth Groups, Volunteers, Local Communities

## MPR 5.5 RCA
(April 2025 - March 2026)
For the month of JANUARY
Organisation: River Cities Alliance
Sl. No. | Activity | Till Dec 25 | 2026-01-26 | Total
1 | Web posts | 52 | 4 | 56
2 | Workshops (excluding 5b /URMP Workshops) | 13 | 0 | 13
3 | Seminar/ Webinar/Meetings | 22 | 6 | 28
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin) | 0 | 0 | 0
| a) Meetings in States | 6 | 0 | 6
| b) Workshops in States | 2 | 0 | 2
6 | Publications | 0 | 0 | 0
| a) Newsletter | 3 | 0 | 3
| b) Others | 12 | 0 | 12
7 | Concept Notes | 7 | 1 | 8
Annexures
List (Type 2,3,4,5) December
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | STC 6.0 Finalists Onboarding Meeting | 3 | Online | 9.01.2026 | 27
2 | STC 6.0 Finalists Inception Meeting | 3 | Online | 21.01.2026 | 20
3 | STC 6.0 Faculty Mentor Meeting | 3 | Online | 29.01.2026 | 13
4 | Webinar on "Citizen Engagement for River Conservation - A Case Study of the 'Cleanup Ramganga' Campaign" | 3 | Online | 19.01.2026 | 35
5 | Webinar on "Natural Capital Accounting and Valuation of Ecosystem Services - A case of Mula Mutha River Catchment, Pune" | 3 | Online | 06.01.2026 | 80
6 | Expert lecture on "Urban water management in India - Transitioning to holistic approach " for students of University of Wisconsin Madison (USA) | 3 | NIUA | 08.01.2026 | 22
7 | Expert lecture on "Principles and techniques of resilient city planning & urban design for Guwahati city " as part of a joint studio for students of SPA Bhopal | 3 | Online | 28.01.2026 | 42
List (Type 1,6) December
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on " Transforming Impervious Urban Spaces into Functional Stormwater Wetlands - A case study of underused asphalt parking lot in Asheville, North Carolina" | 1 | 05.01.2026
2 | Inspirational Monday Series on "Transforming Engineered Riverbanks into Multifunctional Ecological Landscapes - The Case of Weihe Ecological Park, Shaanxi Province, China" | 1 | 12.01.2026
3 | Inspirational Monday Series on "Rainwater Harvesting Theme Parks for Urban Water Resilience - The Case of Hyderabad" | 1 | 12.01.2026
4 | Inspirational Monday Series on Plastic Trapping Using Floating Barriers in the Mithi River, Mumbai – An Initiative by Plastic Fischer, Supported by Planet Wild | 1 | 19.01.2026
List (Type 7) December
Sl. No. | Subject | Type | Date
1 | Concept Note for RamGanga Basin Chapter | 7 | 30.01.2026

## COE-IT BHU
(April 2025 - March 2026)
For the month of January
Smart Laboratory on Clean Rivers
Sl. No. | Activity | Till December-25 | 2026-01-01 | Total
1 | Web posts | 80 | 8 | 88
2 | Workshops / Conference | 6 | 0 | 6
3 | Seminar/ Webinar | 7 | 0 | 7
4 | Exposure Visits | 16 | 2 | 18
5 | URMP Related (Non Ganga Basin) | NA | NA | NA
| a) Meetings in States | NA | NA | NA
| b) Workshops in States | NA | NA | NA
6 | Publications | 0 | 0 | 0
| a) Newsletter | 0 | 0 | 0
| b) Others | 4 | 0 | 4
7 | Consultative Meetings / Interactive Sessions | 15 | 8 | 23
Annexure
List (Type 2,3,5,4)
Sl. No. | Event Topic | Type | Venue | Date/Days/Duration | Number of Participants
1 | Field visit of Director, NMCG, Ministry of Jal Shakti in Varanasi (SLCR project) | Type 4 | Rameshwar | 02.01.2026 | 5+
2 | SLCR Team attended the Innovation Management course organised by the Danida Fellowship Centre (DFC) in Copenhagen, Denmark, from 5 to 16 January 2026, where DSS, SLCR was presented as the target project. | Type 4 | DFC, Copenhagen, Denmark | 12 Days | 23
List (Type 6)
Sl. No. | Subject | Type | Date
1
2
List (Type 7)
Sl. No. | Consultative Meetings / Interactive Sessions | Type | Venue | Date
1 | An interactive session and meeting with the officials of Department of Atomic Energy (DAE): Variable Energy Cyclotron Centre (VECC) Mass Mobilization campaign for the rejuvenation of National River Ganga | Type 7 | Seminar Hall, Department of Civil Engineering, IIT (BHU) | 17.01.2026
2 | An online meeting for presentations by shortlisted participants of the Case study competition focussing on River Health and Assessment organized by the Student wing, SLCR | Type 7 | Deptt. Of Civil Engineering, IIT (BHU) | 19.01.2026
3 | SLCR team visited the DDO & EE Irrigation department, Prayagraj, for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Prayagraj | 20.01.2026
4 | SLCR team had separate meetings with ADPRO, BSA & DIOS, Varanasi for constructions of MAR-Rainwater Harvesting Structures and issuance of NOC | Type 7 | Geoinformatics Lab, Deptt. Of Civil Engineering, IIT (BHU) | 20.01.2026
5 | SLCR -CSE Online meeting regarding Sustainable solutions/technologies for small rivers rejuvenation | Type 7 | Deptt. Of Civil Engineering, IIT (BHU) | 20.01.2026
6 | SLCR -NIUA Online meeting regarding Sustainable solutions/technologies for small rivers rejuvenation | Type 7 | Deptt. Of Civil Engineering, IIT (BHU) | 20.01.2026
7 | SLCR team visited the CDO, Jaunpur, for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Vikas Bhawan, Jaunpur | 21.01.2026
8 | A meeting with Danish Embassy held under the Chairmanship of Secretary (DoWR, RD & GR) to review the progress made under CoE and SLCR | Type 7 | Committee Room at Shram Shakti Bhawan, New Delhi | 27.01.2026