## MPR 1.3_Project_COD effective
MPR 1.3
(April 2026 - March 2027)
For the month (As on 31st July 2026)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | 2024-03-01 | The STP is operational with partial flow. The remaining work of the I&D sewer line is in progress through trenchless pipeline laying. Additional scope variation approved in 71st EC meeting.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | Partial COD declared as 01.02.2026
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | Partial COD declared as 01.01.2026
5 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | COD declared for 8 MLD (Jangipur) COD awaited for 5 MLD Raghunathgunj
6 | I & D and STP at Kota | DBOT | 258.48 | 36 | 2023-06-01 | The STP is operational from Dec-2022 The Project De-scoping is pending
7 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
8 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partial COD declared
9 | I&D with STP works at Sapera Basti, Dehradun | DBOT | 78.99 | 15 |  | Under trial operations
10 | I & D and STP works at Muni ki reti, Neelkanth, Swarg aashram | DBOT | 94.06 | 12.8 |  | Under trial operations (Muni-Ki-Reti and Swargashram) Under Construction (Neelkanth 1.5 MLD)
11 | Interception and diversion of balance discharge of 13 drains and augmentation of Salori STP | DBOT | 331.75 | 43 |  | Under trial operations
12 | I&D and STP Works at Vrindavan | DBOT | 77.7 | 13 | 2026-03-01 | Under trial operations
13 | Interception and Diversion with STP) at Chakdah Municipal Town | DBOT | 121.66 | 15 | trial run started on 14th Feb 2026. | COD awaited
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | Effective date for STP-1 ,2&3 has been declared as 02.03.2026. | Due to pending land NOC the effective date for remaining STPs (STP-4 &5) is yet to be declared.
2 | Interception & Diversion and 60 MLD STP works for Durga Drain at Varanasi | HAM | 274.31 | 60 | 2026-07-01 | The SPV formation has been completed. The Concession Agreement is expected to be executed by 15 August 2026, and the Effective Date is targeted to be declared by 30 September 2026.
3 | Interception & Diversion and STP works at Pt. DDU Chandauli (HAM) | HAM | 262.78 | 45 | 2026-07-01 | The SPV formation has been completed. The Concession Agreement is expected to be executed by 15 August 2026, and the Effective Date is targeted to be declared by 30 September 2026.

## MPR 1.5 Project Engg O&M
Details of Project Engineer Engagement in various STP projects, NMCG (MPR 1.5 - JULY 2026)
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Haridwar STP Project | 68 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | PE contract Completed |  |  |  | O&M
2 | PE Varanasi STP Project | 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
3 | PE Mathura STP Project | 30 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
4 | PE Prayagraj STP project | 14 MLD 42 MLD 16 MLD | M/s. AECOM India Pvt. Ltd. In JV with URS Scott Wilson India Consortium | 2025-03-01 | 2025-03-01 | 2024-08-01 | Mar-25 | O&M | 0.4
5 | PE Kanpur STP project | 30 MLD 15 MLD 5 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-04-01 | 2026-06-01 | Mar-25 | Mar-25 | O&M
6 | PE Howrah, Bally & Baranagar | 65 MLD 40 MLD 60 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | 2025-12-01 | 2025-12-01 | Dec-25 | Dec-25 | O&M
7 | PE Budhana Muzaffarnagar STP Project | 10 MLD 22 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | Jun-25 | Jun-25 | 2023-03-01 | 2025-06-01 | O&M
8 | PE Moradabad STP Project | 25 MLD |  | 2026-02-01 | 2026-06-01 | 2026-02-01 | 2025-05-01 | O&M
9 | PE Mirzapur Ghazipur | 8.5 MLD 8.5 MLD 21 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-06-01 | 2025-12-01 | Apr-26 | O&M
10 | PE Maheshtala STP | 35 MLD | M/s. WAPCOS Limted | 2026-04-01 | 2026-06-01 | Aug-25 | Aug-25 | O&M
11 | PE Bareilly | 42 MLD 20 MLD 1 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | PE contract Completed |  |  |  | O&M
12 | PE Ayodhya | 32 MLD |  | 2026-02-01 | 2026-06-01 | 2026-02-01 | 2026-05-01 | O&M
13 | PE Farrukhabad-Fatehgarh | 30 MLD 20 MLD 2 MLD |  | PE contract Completed |  |  |  | O&M
Total
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.5 Proj engg under progres
Details of Project Engineer Engagement in various STP projects, NMCG (MPR 1.5 - JULY 2026)
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Digha & Kankarbagh STP Project | 150 MLD 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | 2025-12-01 | 2026-04-01 | 2025-06-01 | 2025-06-01 | Under Progress
2 | PE Bhagalpur STP Project | 40 MLD 5 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | 2026-03-01 | 2026-06-01 | 2026-02-01 | 2026-02-01 | Under Progress
3 | PE Agra STP Project | 31 MLD 35 MLD 100 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-06-01 | 2026-06-01 | 2026-04-01 | 2026-06-01 | Under Progress
4 | PE North Barrackpore STP project | 30 MLD 8 MLD | M/s. MaRS Planning & Engineering Services Pvt. Ltd. | 2025-09-01 | 2026-06-01 | 2026-02-01 | 2026-02-01 | Under Progress
5 | PE Meerut STP Project | 220 MLD | M/s. AECOM India Pvt. Ltd. In JV with M/s. PDCOR Limited | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | Under Progress
6 | PE Saharanpur STP Project | 135 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2025-05-01 | 2025-10-01 | 2025-05-01 | 2025-05-01 | Under Progress
7 | PE Garden Reach STP Project | 65 MLD | M/s. Fichtner Consulting Engineers (India) Pvt. Ltd. | 2026-04-01 | 2026-06-01 | 2026-02-01 | 2026-06-01 | Under Progress
8 | PE Gokul Barrage STP Project | 60 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-06-01 | 2026-06-01 | 2026-05-01 | 2026-06-01 | Under Progress
9 | PE Dhanbad STP Project | 18 MLD 21 MLD 75 MLD 60 MLD 18 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2026-04-01 | 2026-04-01 | 2025-04-01 | 2025-04-01 | Under Progress
10 | PE Lucknow STP Project | 100 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-06-01 | 2026-06-01 | 2026-02-01 | 2026-05-01 | Under Progress
11 | Katihar | 55 MLD | [5 empty] | Under Tendering
12 | Aligarh | 113 MLD | [5 empty] | Under Tendering
13 | Siliguri | 49 MLD | [5 empty] | Under Tendering
14 | Moradabad | 80 MLD | [5 empty] | Under Tendering
15 | Durga Drain, Varanasi | 60 MLD | [5 empty] | Under Progress
16 | Pt. DDU Nagar, Chandauli | 45 MLD | [5 empty] | Under Progress
17 | Arrah | 47 MLD | [5 empty] | Under Tendering
Total
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.4_KSDC
MPR 1.4
April 2026 - March 2027
For the month of July 2026
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | Till June, 2026 | July, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 2 | 1 | 3
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) July 2026
S.No | Event Topic | Type | Venue | Date/Days/Duration | No. of Participants
1 | Capacity building program under KSDC | On-site | Haridwar, Rishikesh, Roorkee | 3 | 67
List (Type 1,6) July 2026
| Sl. No. | Subject |  | Date
List (Type 7) July\ 2026
| Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
MPR 3.1
(April 2025 - July 2026)
For the month of July, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Jun-26 | 2026-07-01
1 | STP Inspection Reports Received **
| Uttrakhand | Dec'25 - Mar'26 | -
| Uttar Pradesh | Dec'25 - Mar'26 | -
| Bihar | Dec'25 - Mar'26 | -
| Jharkhand | Dec'25 - Mar'26 | -
| West Bengal | Dec'25 - Mar'26 | -
2 | River water Quality Data Received *
| Uttrakhand | Oct'25- Dec'2025 | Jan'26- Mar'2026
| Uttar Pradesh | Oct'25- Dec'2025 | Jan'26- Mar'2026
| Bihar | Oct'25- Dec'2025 | Jan'26- Mar'2026
| Jharkhand | Oct'25- Dec'2025 | Jan'26- Mar'2026
| West Bengal | Oct'25- Dec'2025 | Jan'26- Mar'2026
3 | GPI Inspection Report received *
A | Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3703 (Ganga: 1296; Yamuna: 2407) | 3703 | 3703
B | Target (9th Round - till 15th Jan2027)
| 3938 (Ganga : 1306 ; Yamuna : 2632) | 921* | 281#
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Dec'2025 | -
| Uttar Pradesh | Jan'25- Dec'2025 | -
| Bihar | Jan'25- Dec'2025 | -
| Jharkhand | Jan'25- Dec'2025 | -
| West Bengal | Jan'25- Dec'2025 | -
5 | Number of Publications/Reports | 65 | 5
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | Review of Gap in data in NWMP-112 MWQM Stations with interstate (UK, UP & Bihar) data for 2024&25. | 2026-07-02
2 | Post Monsoon-2025 Monitoring of Drains in UP (Nov 2025-Feb 2026) discharging in River Ganga and its tributaries (Bijnor-Ghazipur) | 2026-07-08
3 | Post Monsoon-2025 Jt. Monitoring of 30 Drains (Dec. 2025-Feb. 2026) discharging in River RamGanga and its tributaries (Bijnor-Ghazipur) | 2026-07-06
4 | Progress report of NMCG funded projects -PIAS, SER and WQM - Jan-March 2026 | 2026-07-16
5 | Laboratory Audit reports (Draft) of Ganga Main Stem States | 2026-07-17
Annexure A for S.No 3 B
| Total GPIs (9th Round) | 3938
| * Inspected | 921*
| # Reports uploaded on CPCB Portal | 281# | Process of Report review 'In Progress' by SPCBs/ PCCs
| Complied | - | << Total Action Completed Till date
| Non-Complied | - | << Total Action Completed Till date
| Temporary Closed | - | << Total Action Completed Till date
| Permanently Closed | - | << Total Action Completed Till date

## MPR 3.2_Regulatory Cell
MPR 3.2
(April 2026 - March 2027)
For the month of July (As on 31st July 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of June 26 | 12
2 | Application returned back in July 26 | 2
3 | Applications decided in July 26 | 1
4 | New Applications received in July 26 | 4
5 | Pending Application at the end of July 26 | 13
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st April 2026) | 1
(5)= (1)-(2)-(3)+(4)
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/ Return | Cases Recommended
2026-07-23 | 16 | 3 | 2 | Minutes under preparation
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Construction of water intake structure for drawl of water from river Ganag at Mirzapur for meeting requirement of 2*800 MW Ultra Super Critical Thermal Power Project at Mirzapur, U.P. | Mirzapur Thermal Energy (UP) Pvt. Ltd. (Adani Group) | 2026-02-17 | File forwarded to steering committee for their examination on utilization of treated wastewater from nearby STPs under Tariff Policy, 2016.

## MPR 4.1_E-file status
MPR 4.1
eOffice closed files summary
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
1st March 2026 to 31st March 2026 | 0
1st April 2026 to 30th April 2026 | 1
1st May 2026 to 31st May 2026 | 2
1st June 2026 to 30th June 2026 | 2
1st July 2026 to 31st July 2026 | 2
Total | 529
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Total: 69
Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01
Wing/Section/ Unit wise summary from 1st March 2026 till 31st March 2026
i. Nill
Wing/Section/ Unit wise summary from 1st April 2026 till 30th April 2026
i. Communication Wing: 1
Wing/Section/ Unit wise summary from 1st May 2026 till 31st May 2026
i. Communication Wing: 1
ii. O/o ED (Tech): 1
Wing/Section/ Unit wise summary from 1st June 2026 till 30th June 2026
i. HR & Training: 1
ii. O/o ED (Tech): 1
Wing/Section/ Unit wise summary from 1st July 2026 till 31st July 2026
i. SMD Section: 1
ii. O/o ED (Tech): 1

## MPR 5.2_GKC
MPR 5.2
Monthly Progress Report- Gyanganga.ai (July 2026)
Generated on 1st August 2026
Sl. No. | Title | Till 30th June 2026 | 2026-07-01 | FY 2026-27 | Total (as on 31st July 2026)
1 | Total Number Document on GKP | 1408 | 0 | 37 | 1408
2 | Other Literature on River Ganga | 10361 | 20 | 65 | 10381
Categories-wise details of documents uploaded between 1st to 31st July 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 0
Studies/Reports |  | 0
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 0
Maps |  | 0
Total |  | 0
Details of documents uploaded between 1st to 31st July 2026

## MPR 5.3-Prayag status
MPR 5.3
(April 2026 - March 2027)
For the month of July (As on 3rd August 2026)
MPR PRAYAG/ GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status
a | No. of STPs with OCEMS Installed | 282
b | No. of STPs with Flow Data received | 201
c | No. of STPs with Influent Characteristic Data received | 182
d | No. of STPs with Effluent Characteristic Data received | 250
2 | Data Reliability Status
a | No. of STPs with Satisfactory Data received | 236
b | No. of STPs with Poor Data Quality (Annex A1) | 5
c | No. of STPs with No Data Received (Annex A2) | 26
B | OCEMS based results communicated to States till Month | Communicated till July 2026
C | Eflow reports updated till period | Updated till Oct-Dec 2025
D | GDPMS
| No. of Meetings held in July 2026 | 24
| No. of Meetings held in June 2026 | 98
E | PRAYAG_GEO Portal
| No. of Active GIS Layers (Annex B) | 29
| No. of Use Cases | 3
PRAYAG/ Geoportal-MPR July 2026 (Item 5.3, MPR)
Annexure-A
Poor Data
| STP Name | Availability Percent
| 1.5 MLD STP Chutia | 0.76%
| 20 MGD Nilothi Phase II | 13.02%
| 3 MLD STP Firozabad | 17.15%
| 6.5 MLD STP Naihati | 29.79%
| 140 MLD STP Dinapur | 35.35%
No data STPs
| STP Name | State
| 0.66 MGD Molar Band | Delhi
| 11.4 MLD STP Bokaro | Jharkhand
| 2.57 MLD STP Bokaro | Jharkhand
| 1 MLD STP ANUPSHAHAR | Uttar Pradesh
| 1.5 MLD STP Anupshahar (UPJN) | Uttar Pradesh
| 10.445 MLD STP Etawah | Uttar Pradesh
| 100 MLD STP at Noida Sector 168 | Uttar Pradesh
| 120 MLD STP Goitha Varanasi | Uttar Pradesh
| 13.50 MLD STP Tixi Nala | Uttar Pradesh
| 14 MLD STP Baghpat | Uttar Pradesh
| 15 MLD STP Baniyapur UPJN | Uttar Pradesh
| 20 MLD CETP Jajmau | Uttar Pradesh
| 21 MLD STP ETAWAH | Uttar Pradesh
| 21 MLD STP Pakka Bagh | Uttar Pradesh
| 25 MLD STP sector 50 noida | Uttar Pradesh
| 30 MLD STP JAUNPUR | Uttar Pradesh
| 40 MLD STP Mapan | Uttar Pradesh
| 42 MLD STP Sajari | Uttar Pradesh
| 43 MLD STP Salori | Uttar Pradesh
| 7 MLD STP Mirzapur | Uttar Pradesh
| 80 MLD STP Dinapur | Uttar Pradesh
| 26.5 MLD STP at Chinsurah | West Bengal
| 35 MLD STP Maheshtala Waste Water Management Pvt Ltd | West Bengal
| 40 MLD STP at Bally Howarh | West Bengal
| 60 MLD STP Baranagar | West Bengal
| 65 MLD STP Arupara Howrah | West Bengal
Annexure-B Active GIS layer - July 2026 (As on 03.08.2026)
S. No. | Type | GIS Layer
1 | BASIC | Ganga
2 |  | Ganga Centre line SoI
3 |  | Ganga River Basin
4 |  | Popular River
5 |  | Ganga State
6 |  | Ganga Basin Sub District Census
7 |  | Ganga Basin Town Census
8 |  | Census Sub District 2011
9 |  | Census Town 2011
10 | WATER RESOURCES | India River Network
11 |  | Major Aquifers
12 | ECOLOGY | Riverine Wetland (UP/Bihar/Jharkhand)
13 |  | Wetland PAN India (SAC)
14 | RIVER WATER QUALITY | Ganga Polluted Stretch, 2018
15 |  | Ganga Polluted Stretch, 2022
16 |  | Ganga Polluted Stretch, 2023
17 |  | Ganga Polluted Stretch, 2025
18 |  | Manual Water Quality Stations (Locations)
19 |  | RTQMS (Locations)
20 |  | Biomonitoring (Locations) (to be add)
21 | POLLUTION ASPECTS | Sewage Gap Analysis
22 |  | STP (Other than NMCG) (Locations)
23 |  | STP NMCG (Locations)
24 |  | GPIs (Locations)
25 |  | Solid Waste Dumps (IIRS data)
26 | MISC. | Ganga Centre line 1 km points SoI
27 |  | Ganga Final Survey SoI
28 |  | Point outfall 45N SoI
29 |  | Point outfall 44N SoI

## MPR 5.4-Jan Ganga Vertical_Comm
MPR 5.4
(April 2026 - March 2027)
For the Month of July 2026 (As on 1st August 2026)
MPR Communication
| Followers | Till Previous Month-June 2026 | Current Month-July 2026
1 | Twitter | 125552 | 124983
| Facebook | 622655 | 627430
| Instagram | 150296 | 154824
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 205 | 29 | 40 Minutes
| Facebook | 205 | 29 | 40 Minutes
| Instagram | 138 | 34 | 50 Minutes
b) | Rebuttals on | 1
Social Media
c) | Positive Stories | 35 |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 13 |  | Annex A
5 | Publication through PIB
a) | Press Release ( Atleast One per month )
i) | Press Release-Event Based | ETF 2nd July 2026
ii) | Press Release- Success Story | NBS , 9th July 2026
b) | Backgrounder ( One per Quarter ) | Planned for next month
c) | Articles/Op-eds in Newspapers ( One article -Half Yearly) | Work on this is currently in progress
|  | Number of Events | Participation
6 | Events Organised by NMCG |  |  | Annex B
i). | Cleanliness Drives on Yamuna | 4 | Approx. 2000
7 | Events through Partner |  |  | Annex B
a) | DGC & SMCG | 56 | 35116
b) | NGO | Nil | Nil
c) | Institutes | Nil | Nil
| Total | 56 | 35116
8 | Sponsorship | Nil
9 | Capacity Building Training /Workshop (Communication Unit ) | Nil
Annex B
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | 12 years of NMCG | 1st July 2026 | https://x.com/cleanganganmcg/status/2072163769850229012?s=20 | ----------------------- | https://www.instagram.com/reel/DaPErP6vtSo/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
2 | 12 years of NMCG | 02nd July 2026 | https://x.com/cleanganganmcg/status/2072570194338455719?s=20 | https://www.facebook.com/reel/1420316136598600 | https://www.instagram.com/reel/DaR9-buG7s-/?utm_source=ig_web_copy_link
3 | Public review- Banaras | 03rd July 2026 | https://x.com/cleanganganmcg/status/2072964974842912985?s=20 | https://fb.watch/ICVmZysNrJ/ | https://www.instagram.com/reel/DaUxV8bkh9J/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
4 | Project update- Haridwar | 03rd July 2026 | https://x.com/cleanganganmcg/status/2073033728771936583?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02nCCHCTm1Roh73FgCEgC2HzEr7M15DC6u8Y4EFNhfRk9ii2EYWA4CDUGGSNpi6i3Zl | https://www.instagram.com/p/DaVQ2Qrj2gE/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
5 | 12 Years of NMCG | 07th July 2026 | https://x.com/cleanganganmcg/status/2074375031006892182?s=20 | https://www.facebook.com/reel/1668429697610295 | https://www.instagram.com/reel/DaeyuJBk6EW/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
6 | Rebuttal Post- 3.5 MLD STP Rishikesh | 07th July 2026 | https://x.com/cleanganganmcg/status/2074439171746447390?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02grNAkFwHoYQmViWFEgc2z2cfbZZGdu3nx5HP4LMUhLdhmANaESUjHxGXLfSMdP1Yl | https://www.instagram.com/p/Dafq3WVj9va/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
7 | Project Update Rishikesh | 07th July 2026 | https://x.com/cleanganganmcg/status/2074491185863987603?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid037CLtTnYYY2JJGPPjsBUgPbmQgUGYhPUYebUAG1LpL4AqY5ocDMMkmQCeZXGUV8eMl | https://www.instagram.com/p/DafnoMdj-lJ/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
8 | Cleanliness drive- Varanasi | 08th July 2026 | https://x.com/cleanganganmcg/status/2074868204602855834?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0kTqDsS4Hgw8yRtg7NkpZv2omuUR7k26VeUcH1usyEkq6Z2TLsNWhwJ5vrcDww9Wul | https://www.instagram.com/p/Dah2o6pktZ_/?utm_source=ig_web_copy_link
9 | 12 Years of NMCG | 09th July 2026 | https://x.com/cleanganganmcg/status/2075084944918069644?s=20 | https://www.facebook.com/reel/1763008691382061 | https://www.instagram.com/reel/Daj10dIEux0/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
10 | Public review- Patna | 09th July 2026 | https://x.com/cleanganganmcg/status/2075154698148233295?s=20 | https://www.facebook.com/reel/1697860912006814 | https://www.instagram.com/reel/DakU4wJFeQ4/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
11 | Project update- Uttarkashi | 10th July 2026 | https://x.com/cleanganganmcg/status/2075546845489811912?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0GaebJKwcPcRXvNA9qa9EzVh5q2yqgvfwBzb9j1WEE4GQSh8C5a8MFkqnBe6uxSbZl | https://www.instagram.com/p/DanH5H8AB0o/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
12 | STP Story- 100 MLD Bihar | 12th July 2026 | https://x.com/cleanganganmcg/status/2076283096027279416?s=20 | https://facebook.com/reel/1017987024162240/ | https://www.instagram.com/p/DapdH4UD35f/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
13 | Biodiversity- Meerut | 13th July 2026 | https://x.com/cleanganganmcg/status/2076529400183714213?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0kt5QrRcFneLqu3EiGPsu5dVrbUCK6cYKt1m5v9ZcTd2kXUpcccevFNppePM4iXRAl | https://www.instagram.com/reel/DauIY34sr_p/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
14 | Wetlands | 13th July 2026 | https://x.com/cleanganganmcg/status/2076540640717132142?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid022jdEdeqWpYkCuv7Jf1A6sS4xsHfxeU2sZNEUPL5D2CFtacRLo4R2VPgRroz368V3l | https://www.instagram.com/p/DauLtkwMV4m/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
15 | Wetlands | 13th July 2026 | https://x.com/cleanganganmcg/status/2076641525371691130?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0DPY9SofcoesfpyHARGuvmtTS2DHcGbiwjPFJUeQv4gLKbDpDbRqew6P6LGp6kN8gl | https://www.instagram.com/reel/Dau5gQMA0Q-/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
16 | Wetlands | 14th July 2026 | https://x.com/cleanganganmcg/status/2076905519210778777?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02dPRHpas5Sbbr4Y7iP3ZBRdsuH1NrH4ZrHFZ2GHUMcDFXHvyNfM67PQq8zkfaBBHpl | https://www.instagram.com/reel/DawvhrdsESf/?utm_source=ig_web_copy_link
17 | City level action plan for reuse of treated water- Varanasi | 14th July 2026 | https://x.com/cleanganganmcg/status/2076985957535150150?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0291d6xP1SuxMeR6aEvg5LjhZRqNwAgs9qoG7CAzLnZcrP6Gvxzp83GuzYYVQheQW6l | https://www.instagram.com/reel/DaxWsiWPVnI/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
18 | 71st EC Meeting | 14th July 2026 | https://x.com/cleanganganmcg/status/2076996338370465820?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02sgYS5Ep3d9PcMM8CwsP5Xfxw97GCQk8WKUXzdy5hRUmHBooAssfe8D8gPzV2BnHGl | ----------------------------
19 | Wetlands | 15th July 2026 | https://x.com/cleanganganmcg/status/2077316816146510335?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0g6FGS5ChrZwDN3jaoS6cL7od34z9MSQ7XZ6A8UXLzH7RjqJTJZmaNPdb9y9qq5w2l | https://www.instagram.com/p/DazsmGlAXhY/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
20 | Project update- Meerut | 16th July 2026 | https://x.com/cleanganganmcg/status/2077611092252246322?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0WLyVbq48mu83fx3kRsoZAFvh5Fj7tMHsps5fABUBwJk3JyjMprh9t6cexjhTkPNal | https://www.instagram.com/p/Da12Ae-jIo1/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
21 | Drain tapping- Kanpur | 16th July 2026 | https://x.com/cleanganganmcg/status/2077676414820815136?s=20 | https://facebook.com/reel/1556690389104739/
22 | Ek din ek ghanta ek sath-Cleanliness drive- | 19th July 2026 | https://x.com/cleanganganmcg/status/2078772715411132859?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0CvTF5JrQjByRX8yJ4mrgGrYmyM1bUTAi9xa79aRvpUVUXpRfMxoLTxStgc1kf2R2l | https://www.instagram.com/p/Da-AcuYDxW5/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
23 | Cleanliness drive- Bihar | 20th July 2026 | https://x.com/cleanganganmcg/status/2079074548826435882?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02fnLNkNtQL4Juvv1bH4Vb1snBgKh1UC7SKLAegC3teMvtCEr3PF1wS6qQoAJtNj8Dl | https://www.instagram.com/p/DbAMGWLDODy/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
24 | Project update - Kanpur | 20th July 2026 | https://x.com/cleanganganmcg/status/2079153981037949426?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0R5J5hKurRpSUdgsaq5QHo34Dk9XVrA5XwtU6YCrRL83vXEtgL22VW7JhhwU8qTuJl | https://www.instagram.com/reel/DbAwuNXgMaE/?utm_source=ig_web_copy_link
25 | Dolphin rescue | 21st July 2026 | https://x.com/cleanganganmcg/status/2079518172542378021?s=20 | https://facebook.com/reel/1500220331426892/ | https://www.instagram.com/p/DbDfJm5j59C/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
26 | Project update- Unnao | 22nd July 2026 | https://x.com/cleanganganmcg/status/2079900559990206907?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02jfXSf3WancTvxSz4n8kmRHwiv5At3SLcuCrAawyg15p6iAnSvYbCv2YicsNnrvrHl | https://www.instagram.com/reel/DbGDW3yPK5g/?utm_source=ig_web_copy_link
27 | Wetlands | 23rd July 2026 | https://x.com/cleanganganmcg/status/2080137414358728829?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02y8hsrj8VR84QyQerophe1Q9hxMmRv7xvQGRtR3HMTVZ6bAqGd7f5boVLorE3dndml | https://www.instagram.com/reel/DbHwezhIGqc/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
28 | Safe Reuse of Treated Waste Water | 24th July 2026 | https://x.com/cleanganganmcg/status/2080502947725656432?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid05jbgLxfkywA8GN2fAkDP5GSkDup9YUALUdPbbwEFg5sNd94em5ajxiqJawUWPpjFl | https://www.instagram.com/reel/DbKW8gpvyzs/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
29 | Public review- Prayagraj | 24th July 2026 | https://x.com/cleanganganmcg/status/2080516923759247464?s=20 | https://facebook.com/reel/1060450369669945/ | https://www.instagram.com/reel/DbKkXYIPiQ_/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
30 | 4O MLD TTP Bingwana, Kanpur | 24th July 2026 | https://x.com/cleanganganmcg/status/2080548563386560917?s=20 | https://facebook.com/reel/4362828027366735/ | https://www.instagram.com/reel/DbKshAJPpC8/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
31 | Project update- Prayagraj | 24th July 2026 | https://x.com/cleanganganmcg/status/2080601512368365860?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02mvLaNE3arBJDH44ku9fHeM3BEvxDx887xD7cq8VSJZ3xVEWSxMzcTohyHB4AJUbl | https://www.instagram.com/reel/DbLHlVYvzrH/?utm_source=ig_web_copy_link
32 | Public review- Banaras | 27th July 2026 | https://x.com/cleanganganmcg/status/2081655026888695858?s=20 | https://www.facebook.com/share/r/1KYpZGyYUY/ | https://www.instagram.com/reel/DbSg99vMNzz/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
33 | Safe reuse of treated waste water adopted | 28th July 2026 | https://x.com/cleanganganmcg/status/2082079984806772834?s=20 | https://www.facebook.com/share/p/196Qm9PVE7/ | https://www.instagram.com/reel/DbVigwoMr-i/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
34 | Project Update Banaras | 31st July 2026 | https://x.com/cleanganganmcg/status/2083058941928554506?s=20 | https://www.facebook.com/share/p/18hagBPZF3/ | https://www.instagram.com/p/DbcgN0zjMvM/?igsh=NmdmeGtva2c3d2Fi
35 | A New Approach to River Rejuvenation: Nature-Based Solutions Will Restore the Betwa's Continuous Flow | 2nd July
36 | Kashi Emerges as a Haven for Ganga Dolphins | 3rd July
37 | AI Will Help Identify Precise Sites for Groundwater Recharge | 4th July
38 | Agra to Use Treated Wastewater for Irrigation and at Metro Stations | 7th July
39 | Namami Gange Integrates Sewerage Systems in Three Uttarakhand Towns | 9th July
40 | NMCG Launches Constructed Wetland Projects for Yamuna Drain Cleanup | 10th July
41 | Namami Gange: Uttarkashi's Sewerage Network Emerges as a Key Link in Ganga Conservation | 11th July
42 | Namami Gange to Restore Five Wetland Sites Across the Ganga Basin | 13th July
43 | Varanasi Becomes UP's Third City to Implement a Wastewater Management System | 14th July
44 | NMCG: Ganga's Cleanliness Depends on the Entire River Basin, Not Just Riverbank Cities | 17th July
45 | NMCG Introduces Draft Framework for Small River Rejuvenation | 18th July
46 | Dolphin Rescue Ambulance Turns Every Rescue Mission into a Success | 21st July
47 | Namami Gange Promotes Nature-Based Solutions for Drain Water Treatment | 24th July
48 | Jal Shakti Minister Shri C.R. Paatil chairs 19th Meeting of Empowered Task Force on Ganga Rejuvenation | 2nd July | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2280512&reg=3&lang=1 | PIB Release
49 | NMCG's focus on Nature Based Solutions: Initiation of two pilot projects and training programs on NbS | 9th July | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2282711&reg=3&lang=1 | PIB Release
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Kalindi Kunj , Yamuneshwar Ghat , Geeta Colony , Sonia Vihar | NGOs- YSS Foundation, Yuva Parivartan Foundation, Friends of Yamuna Swachh Yamuna Abhiyaan, Aanchal Foundation; Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
UTTARAKHAND
2 | Plantation Drives & Pledge | DGCs- Uttarkashi, Pauri, Narayan Nagar (Didihat), Ramnagar, Mazra Mahadev, Thalisian, Prabau, Gopeshwar, Chandrabani, Agastyamuni, Maldevta, Banas Paithani, Naikhani, Bal Ganga Sendul Kamer, Phoenics University (Roorkee), Lohaghat, Jwalapur, Rudraprayag, Bageshwar, Pithoragarh, Nainital & Chamoli | 22nd & 23rd July 2026 | Various Locations | College Students, teachers, forest department, youth groups, NGOs, volunteers & local communities
3 | Cleanliness drives, competitions & signature campaigns | Chandrabani, Majra Mahadev, Thalisian, Didihat & Banas Paithani | 22nd - 23rd July 2026 | Different places | School & college students, youth groups & volunteers
UTTAR PRADESH
4 | Van Mahotsav | DGCs & Forest Departments- Lalitpur (Govind Sagar Dam), Chitrakoot (Ranipur Tiger Reserve), Mau (Rajan College of Education), Jhansi (RLB Medical College), Sonbhadra (SBR Campus), Kasganj (New Police Line), Rampur (Ganga Ghats, Milak Swar), Maharajganj (22nd Battalion SSB) & Bahraich | 1st - 7th July 2026 | various locations, areas designated by ditsrict forest areas, schools, colleges, community parks and other strategic places | DM, MLA, CDO, DFO, SDO, Forest Department, District Administration, Acacdemic Institutions & volunteers
5 | Plantation drives, sapling distributions & nursery inspections | DGCs- Bulandshahr, Auraiya, Lalitpur, Chitrakoot, Bharaiach, Rampur & Sonbhadra | 6th - 9th July 2026 | various locations, areas designated by ditsrict forest areas, schools, colleges, community parks and other strategic places | Gram panchayat, nagar nigam, schools, women groups, NGOs and volunteers
6 | Ek Ped Maa Ke Naam & plantation campaigns | DGCs & Forest Departments- Mau , Lakhimpur Kheri , Lalitpur & Muzzaffarnagar | 15th -23rd July 2026 | Shaheed Inter College,Seth Ghat, Mahadev Temple Campus and other various locations | DGCs, forest departments, academic institutions, Ngos, gram panchayats & villages
7 | Cleanliness drives & shramdaan | DGC- Rampur, Farukkhabad, Mau & Kanpur | 23rd -25th July 2026 | Ganga Ghats, near riverbanks, schools & college premises, community halls and other strategic places | DGCs, nagar nigam, youth volunteers & local communities
8 | Awareness drives, cultural programs & Aarti | DGC- Mau and different academic institutions (schools & colleges) | 15 Days campaign | Academic Institutions | Students, teachers, youth groups & local communities
9 | Seminar on Groundwater Conservation & River Rejuvenation | SMCG- UP (Indira Gandhi Pratisthan Lucknow), Water Resources & Ground Water Department, DGCs- Kanpur & Jhansi | 18th - 22nd July 2026 | Lucknow, Kanpur ,Jhansi | SMCG-UP, DGCs, State Water Resource & other Departments and experts
10 | 1 Hour Shramdan Drive | DGC- Rampur (Kosi Ghat, Ram Ganga Ghat, Shahbad Road Talab & Gram Surajganj & other strategic locations) | Every Sunday | Ganga Ghats, near riverbanks, schools & college premises, community halls and other strategic places | School/College Students, Youth, Volunteers, NGO representatives & local communities
BIHAR
11 | Awareness & Cleanliness Campaign ( Cleanliness drives, nukkad natak & swachhta shapath) | DGC-Madhubani (Utkramit Uchh Vidhyalaya, Salha) & Siwan (Rajbanshi Devi High School) | 4th , 13th & 18th July 2026 | different places (indoor/outside venues, academic institutions, Ghats) | School students, teachers, NCC/NSS, youth groups & volunteers
12 | Seminar & Competitions | DGC- Madhubani | 13th to 18th July 2026 | Uchh Madyamik Vidhyalaya, Rampatti | Students, teachers & volunteers
13 | Cleanliness Campaign, Cultural programs & Aarti | DGC- Hajipur | 29th June to 20th July 2026 | Kamhara, Namami Gange Ghat | Nagar parishad, block members, NGOs, volunteers & local communities
JHARKHAND
14 | Cleanliness drives | DGC & nagar parishad, Ramgarh | 7th - 14th July 2026 | Chingara, Patratu, Court campus Chhatramandu | DGC, nagar parishad representatives, school & college students, voulnteers & local communities
15 | Ghat par Yoga | DGC, Nagar parishad, Sahibganj | 20th -28th July 2026 | Mukteshwar Dham Ghat | Academic institutions, community based organisations, volunteers & local communities
16 | Ganga Aarti | DGCs- Ramgarh & Sahibganj | Different Dates | Ganga Ghats | Youth groups, religious leaders, devotees & local communities
WEST BENGAL
17 | Awareness Generation Programme on the Conservation and Protection of Aquatic Biodiversity (Gangetic Dolphin, Gharial and Hilsa Fish) | DGC Malda | 2nd July,2026 | Sukanta Bhawan, Kaliachak-II Development Block Office, Kaliachak-II Development Block, Malda | Block Administration Officers & Staffs, experts from WWF- India, Officers of the Fisheries Department, Forest Department, West Bengal Zoo Authority and Local fishermen
18 | Shramdaan (Cleanliness Drive) | DGC Malda | 2nd July,2026 | i. Mothabari Chowrangi More ii. Mothabari Rickshaw Stand iii. Mothabrai Market Area iv. Premises of Kaliachak-II Development Block Office, Kaliachak-II Development Block, Malda | Block Administration Officers & Staffs, Village Resource Persons (VRPs), Self Help Groups and Community Members.
19 | Community Outreach Programme (Cleanliness Drive, Sapling Plantation and Dustbin Distribution etc.) | DGC Malda | 7th July,2026 | Khejuria Ganga Ghat (Near Farakka Baridge), Kaliachak-III Development Block, Malda | Officials and Staffs of Block, Members of Gram Panchayat , Village Resource Persons (VRPs), Ganga Volunteers, School & College Students and Community Members.
20 | Ganga Aarti | DGC Malda | 7th July,2026 | Parlalpur Mandir Ghat, Kaliachak-III Development Block, Malda | Officials and Staffs of Block, Members of Gram Panchayat, Village Resource Persons (VRPs), Ganga Volunteers, School & College Students, Local Stakeholders, and Community Members.
21 | Mass Awareness Exhibition Stall,2026 | DGC Hooghly | 18th July,2026 to 22nd July, 2026 | Mahesh,G.T. Road,Serampore Municipal Area,Hooghly | Visitors,Local People and Devotees

## MPR 5.5 RCA
MPR 5.5
(April 2025 - March 2026)
For the month of JULY
Organisation: River Cities Alliance
Sl. No. | Activity | Till Jun 2026 | 2026-07-26 | Total
1 | Web posts | 100 | 8 | 108
2 | Workshops (excluding 5b /URMP Workshops) | 19 | 4 | 23
3 | Seminar/ Webinar/Meetings | 48 | 3 | 51
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 7 | 0 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 5 | 0 | 5
| b) Others | 23 | 0 | 23
7 | Concept Notes | 9 | 0 | 9
8 | Demands Received
| a) Cities | 14 | 0 | 14
| b) Academia | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) March
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Webinar on 'Riparian Buffer Zones (RBZ) in Urban River Management Plans' | 3 | Online | 1.07.2026 | 137
2 | "Grand Finale of Student Thesis Competition on ""Re-imagining Urban Rivers"" (Season 6) " | 2 | SPA Bhopal | 23.07.2026 - 24.07.2026 | 90+
3 | Certificate Training Program on 'Circular Water Economy' as part of Student Thesis Competition on ""Re-imagining Urban Rivers"" (Season 6) " | 2 | SPA Bhopal | 23.07.2026 | 34
4 | Certificate Training Program on 'Innovative Approaches for Groundwater Management' as part of Student Thesis Competition on ""Re-imagining Urban Rivers"" (Season 6) " | 2 | SPA Bhopal | 23.07.2026 | 28
5 | Certificate Training Program on 'Evidence Based Planning and Assessment for Urban Water Systems' as part of Student Thesis Competition on ""Re-imagining Urban Rivers"" (Season 6) " | 2 | SPA Bhopal | 23.07.2026 | 32
6 | Lecture at SCET Surat on 'River as a Connected System' as part of the course ' Principles of Urban River Management' | 3 | Online | 16.07.2026 | 22
7 | Eco Friendly Waterfront Development Course - First Lecture on 'Urban Water Ecosystem' | 3 | SPA Bhopal | 21.07.2026 | 19
List (Type 1,6) March
Sl. No. | Subject | Type | Date
1 | Quiz series 21: Rivers, Cities, and Answers | 1 | 01.07.2026
2 | Inspirational Monday Series on "Resilient River Ghod Program " | 1 | 06.07.2026
3 | Inspirational Monday Series on "Multifunctional Watersensitive Playground Landscape in Chennai" | 1 | 13.07.2026
4 | Quiz series 22: Rivers, Cities, and Answers | 1 | 15.07.2026
5 | Inspirational Monday Series on "Kazhipattur Lake restoration, Chennai" | 1 | 20.07.2026
6 | Quiz series 23: Rivers, Cities, and Answers | 1 | 22.07.2026
7 | Inspirational Monday Series on "Ganglav Talav Restoration, Jodhpur" | 1 | 27.07.2026
8 | Quiz series 24: Rivers, Cities, and Answers | 1 | 29.07.2026
List (Type 7) March
Sl. No. | Subject | Type | Date
Demands for RCA (Type 8) March
Sl. No. | Subject | Type | Date
1 |  | 8a
2 |  | 8a
3 |  | 8a

## MPR 5.6 COE-IT BHU
(April 2026 - March 2027)
For the month of July
Smart Laboratory on Clean Rivers (MPR 5.6a)
Sl. No. | Activity | Till Jun-26 (A) | Jul-26 (B) | Total (A+B) | FY 26-27
1 | Workshops / Conference - Organised | 7 | 2 | 9 | 4
2 | Capacity Building Workshops - Organised | 6 | 1 | 7 | 3
3 | Publications | 0 | 0 | 0 | 0
4 | STP Performance Evaluation (Number of STPs) | 12 | 0 | 0 | 5
5 | DSS Project (Physical progress %) | 70% | 6% | 76% | 16%
5a | No. Draft Modules Finalized | 10 | 0 | 0 | 0
6 | Characterisation of Emerging Pollutants (Physical progress %) | 65% | 1% | 66% | 3%
6a | No. of Draft SOPs Finalized | 5 | 3 | 8 | 3
7 | Hydrogeological Model of Varuna Basin for MAR sites (Physical progress %) | 70% | 6% | 76% | 15%
7a | No. of Sites implemented | 0 | 0 | 0 | 0
Annexure
List (Type 1, 2)
Sl. No. | Event Topic | Type | Venue | Date/Days/ Duration | Number of Participants
1 | Application of the Transient Electromagnetic (TEM) Method in Groundwater Studies and Aquifer Mapping | Type 2 | Dev & Vardhana, IIT (BHU) | 27.07.2026 (1 Day) | 52
2 | Lecture series on River ecology and biodiversity: Assessment, interpretation, challenges and restoration | Type 1 | Seminar Hall, IIT (BHU) | 28.07.2026 (1 Day) | 26
3 | 2-days Executive Workshop on Sustainable Sewage Treatment | Type 1 | Dev & Vardhana, IIT (BHU) | 30.07.2026 & 31.07.2026 (2 Days) | 75
List (Type 3)
Sl. No. | Name of Publication | Date | Submitted
List (Type 4)
Sl. No. | Name of STP | Date visited | Report submitted
1 |  |  | -
2 |  |  | -
List (Type 5, 6, 7,)
Sl. No. | Project Details | Type | Activities
1 | DSS Project | Type 5 | A detailed meeting was held with the NMCG Project Wing to review the functionalities of the Decision Support System (DSS). Based on the suggestions and feedback provided by NMCG officials, enhancements are currently being incorporated into the existing STP modules. Simultaneously, a comprehensive user management framework for the Varuna DSS is under development. In addition, all developed modules have been successfully integrated into the DSS, along with an enhanced report generation feature.
2 | Characterisation of Emerging Pollutants | Type 6 | Optimization work is currently underway on the remediation of pharmaceutical contaminants utilizing sewage sludge-based material. Standard Operating Procedure (SOP) drafts for Carbamazepine, Trimethoprim, and Celecoxib have been finalized.
3 | Hydrogeological Model of Varuna Basin for MAR sites | Type 7 | The sTEM survey has been completed. The acquired geophysical data are currently undergoing processing and analysis for aquifer characterization, aquifer mapping, and groundwater model development. The tender process for the construction of the MAR structures has been completed.
List (Type 5a, 6a, 7a)
Sl. No. | Draft Finalized | Type | Comments
1 | SOPs for Carbamazepine, Trimethoprim and Celecoxib | Type 6a | Draft SOPs for Carbamazepine,Trimethoprim and Celecoxib are being finalized and will be submitted to NMCG by first week of August 2026.
2 | Five SOPs, namely Diclofenac, Eplerenone, Telmisartan, Ethofumesate, and Metformin | Type 6a | SoPs were submitted to NMCG, comments have been received from CPCB, and the updated SOPs will be submitted by first week of August 2026.

## MPR 5.6 COE-IIT Delhi
(April 2025 - July 2026)
For the month of July 2026
India-Netherlands Centre of Excellence on Water (MPR 5.6b)
Sl. No. | Activity | Till Jun-26 | 2026-07-01
1 | Workshops / Conference Organised | 9 | 0
2 | Capacity Building Workshops | 0 | 0
3 | Publications | 2 | 0
4 | STP Performance Evaluation (No of STPs) | 2 | 0
5 | Digital Twin project | 0 | 0
6 | Web Posts | 99 | 2
7 | Outreach | 4 | 0
Note | Financial Year (26-27) Funds have not been received.
Annexure
List (Type 1,2)
Sl. No. | Event Topic | Type | Venue | Number of Participants
List (Type 3)
Sl. No. | Title | Date of Submission
List (Type 4)
Sl. No. | Name of STP | Date Visited | Report submitted
List (Type 5)
Sl. No. | Details | Remarks
List (Type 7)
Sl. No. | Topic | Category